{"text_format":"1","workbook":"xlsx","n_sheets":7,"sheets":["1904.1 MR","Stats","Chart detailed","Status change flow","Tools","Parameters","Values"],"not_rendered":{"charts":3,"images":1,"macros":1,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[{"sheet":"Chart detailed","index":2,"reason":"not_a_worksheet"}],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"1904.1 MR","index":0,"n_rows":316,"n_cols":31,"rows_kept":316,"cut":false,"hidden":false,"merged":[]}
["Comment\nNumber","TF?/WG/C?","Comment\nStatus","Resolution\nStatus","Commenter\nSatisfaction","Comment\nCategory","Comment\nType","Required","Page #","Clause","Sub-clause","Line #","Comment","Proposed\nChange","Commenter\nName","Commenter\nAffiliation","Commenter\nEmail","Commenter\nPhone","Comment\nResolution","Last modified on","Comment ID","Role","Style","Index #","Classification","Vote","File","Disposition Status","Other1","Other2","Other3"]
["20130628_1555","Maintenance","New","None","None",null,"Technical","No",51,6,"6.5.2.1.1",null,"IETF RFC 4443 is not included in the list of normative references. ","Add \"IETF RFC 4443 (March 2006), <i>Internet Control Message Protocol (ICMPv6) for the Internet Protocol Version 6 (IPv6) Specification</i>, A. Conta, S. Deering, M. Gupta\" into Clause 2 in the correct location (after IETF RFC 4115) ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1555"]
["20130628_1602","Maintenance","New","None","None",null,"Technical","No",111,7,"7.3.2.2",null,"In Table 7-30, the content of field Description contains reference to \"mode with stripping I-Tag\", whereas the Modifier action clearly shows \"[mi]: REMOVE (B_TAG)\".\nThe text should speak therefore of \"stripping B-Tag\" instead\n","Change \"I-Tag\" to \"B-Tag\" in the selected text","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1602"]
["20130628_1607","Maintenance","New","None","None",null,"Technical","No",111,7,"7.3.2.2",null,"In Table 7-30, the text \"implements the PBB  encapsulation \" references PBB, which is never defined.","[1] Add definition of PBB into 3.2 as follows: PBB: Provider Backbone Bridging \n[2] Modify the selected text in Table 7-30 to read \"implements the Provider Backbone Bridging (PBB) encapsulation \"","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1607"]
["20130628_1610","Maintenance","New","None","None",null,"Technical","No",111,7,"7.3.2.3",null,"In Table 7-30, the text \"If provisioned, this set of rules implements the PBB encapsulation mode with stripping B-Tag and I-Tag .\" makes reference to \"I-Tag\" which is not defined anywhere. It should be \"I-Header\"","Change the selected text to read \"If provisioned, this set of rules implements the PBB encapsulation mode with stripping B-Tag and I-Header.","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1610"]
["20130628_1630","Maintenance","New","None","None",null,"Technical","No",166,8,"8.5.1",null,"\"The ONU does not process the collected data in any way. The ONU does not keep performance monitoring data for any earlier performance monitoring period but the last one (within the history bin). All data processing on the collected performance monitoring data is performed at the OLT or Element Management System.\" - we use NMS (in the meaning of Network Management System) elsewhere in the standard. ","Change \"Element Management System\" to \"NMS\" for consistency","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1630"]
["20130628_1633","Maintenance","New","None","None",null,"Technical","No",166,8,"8.5.1",null,"\"The ONU does not process the collected data in any way. The ONU does not keep performance monitoring data for any earlier performance monitoring period but the last one (within the history bin). All data processing on the collected performance monitoring data is performed at the OLT or Element Management System.\" - we use NMS (in the meaning of Network Management System) elsewhere in the standard. ","Change \"Element Management System\" to \"NMS\" for consistency","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 1633"]
["20130628_2328","Maintenance","New","None","None",null,"Technical","No",642,14,"14.4.3.9.1",null,"IEEE Std 1588v2 is missing in normative references right now. It needs to be fixed. ","Insert the following reference into Clause 2: \"IEEE Std 1588(tm)-2008, Standard for a Precision Clock Synchronization Protocol for Networked Measurement and Control Systems (also known as IEEE Std 1588v2)\"","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130628 2328"]
["20130811_1623","Maintenance","New","None","None",null,"Technical","No",661,"4A","4A.2.3",null,"AU-RF4 is really the OLT requirement and not the ONU requirement. The original text in 8.4.1.2 reads: \"The OLT shall not provision a queue threshold size that is less than the maximum frame size. \"","Remove AU-RF4 but keep AU-RF5 as it is (do not renumber) Insert AT-RF3 with the description copied from AU-RF4","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669",null,"20130811 1623"]
["20130822_1851","Maintenance","New","None","None",null,"Technical","No",6,2,2,null,"MEF 6 and MEF 6.1 are not mentioned in the body of the standard anywhere apart from entries in Clause 2. As such, they do not need to be listed at all. ","Remove entries for MEF 6 and MEF 6.1, and move footnote 7 reference to MEF 10.2 (the line following MEF 6.1 entry)","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130822_1900","Maintenance","New","None","None",null,"Technical","No",459,14,"14.2.2.11",null,"Attribute aOnuCapabilitiesPwrSav contains sub-attribute sVenSpecFieldSize, defining the size of the sVenSpecField. The value of sVenSpecFieldSize can be derived from the Length field value. The sVenSpecFieldSize sub-attribute is therefore unnecessary. ","Implement the following changes:\n[1] Remove \"sVenSpecFieldSize, \" from the list of sub-attributes in paragraph 1 [2] Remove definition of aOnuCapabilitiesPwrSav.sVenSpecFieldSize sub-attribute [3] remove VenSpecFieldSize field in Table 14-19 [4] modify definition of Length field value to read as follows: The size of TLV fields following the Length field, calculated as follows: 3 + N, where N = length of <c>VenSpecField</c> field\n\n<c></c> designates test in Courier New font\n\nImpact = A change in OAM is needed. This would likely involve a new OAM version (see Table 13-15 - new OAM version 0x11) for Package C. ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130822_1903","Maintenance","New","None","None",null,"Technical","No",405,13,"13.3.3.6.4",null,"\"Additionally, the ResponseCode field is used to indicate whether ...\" - text contains reference to ResponseCode field, which does not exist in Table 13-64. ResponseCode ought to be ErrorStatus.","Change ResponseCode to <c>ErrorStatus</c>\nText in <c></c> needs to be written in Courier New font. \n\nImpact = None, this is document management change","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130827_1921","Maintenance","New","None","None",null,"Technical","No",637,14,"14.4.3.7.5",null,"The definition of sub-attribute aQueueColorMarking.sFieldCode points to Table 14-220 for individual values. However, just pointing to Table 14-220 here is not sufficient, because that table provides numerical equivalents for various options, but does not explain what each value means or what exact field it represents. \n\nNOTE: Page reference is valid for D3.4\n","We have two options available. \n\nOption 1: in the aQueueColorMarking.sFieldCode definition, we need to have here a complete text as in Sub-attribute aRuleSetConfig.sClause.sFieldCode (14.4.3.6.1.1).  \n\nOption 2: Just reference the sub-attribute aRuleSetConfig.sClause.sFieldCode (14.4.3.6.1.1). \n\nMy personal preference is for Option 2. \n\nThus the sentence \n\n\"Individual values for the FieldCode field are defined in Table 14-220.\" \n\nshould be replaced with\n\n\"Individual values for the sFieldCode sub-attribute are as defined for sub-attribute aRuleSetConfig.sClause.sFieldCode (14.4.3.6.1.1).\"\n\nMake sure the cross reference is live and proper text style is used. \n\nImpact = None, it is only clarification for textual description. ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130827_1932","Maintenance","New","None","None",null,"Technical","No",603,14,"14.4.3.3.42",null,"The object context for aCounterRxFramesL2CP attribute is wrong. It is ONU, whereas it ought to be PON / UNI Port \n\nNOTE: Page reference is valid for D3.4","Change \n\n\"The aCounterRxFramesL2CP attribute is associated with the ONU object ... \"\n\nto \n\n\"The aCounterRxFramesL2CP attribute is associated with the UNI Port or PON Port object ... \"\n\nImpact = The existing object context definition is just wrong. A new firmware version will have to be created and pushed to devices. ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130828_2024","Maintenance","New","None","None",null,"Technical","No",642,14,"14.4.3.9.1",null,"Currently, in several locations in the draft we have reference to \"IEEE Std 1588v2\", which is not in the list of normative references included in Clause 2. I assume that we actually mean \"IEEE Std 1588-2008\", which is the updated version of the original 1588 standard\n\nNOTE: Page and line reference valid for D3.4","1) Add a normative reference to Clause for IEEE Std 1588-2008, with the following text:\n\"IEEE Std 1588(tm)-2008, IEEE Standard for a Precision Clock Synchronization Protocol for Networked Measurement and Control Systems\n2) Add a definition in 3.3 for “IEEE 1588v2” with the following text: \"<b>IEEE 1588v2</b>: represents a shortcut notation for IEEE Std 1588(tm)-2008\"\n3) Replace all 6 instances of \"IEEE Std 1588v2\" with \"IEEE 1588v2\"\n\nImpact = None, it is only clarification for existing normative reference\n","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20130924_0355","Maintenance","New","None","None",null,"Technical","No",572,14,"14.4.3.2.2",null,"There are a number of issues with this attribute.\n\n1) The context of the object is ambiguous.   Attribute name aUniDynMacAgeLimit indicates UNI context.  The description of this attribute indicates it should be ONU context.  DPoEv2.0 OAM specification indicates the ONU context is correct.\n\n2) Description is incorrect for this object.  Description indicates that the attribute represents the \"maximum size of the MAC address learning table..\"\n\n3) The name of the attribute should also be changed in Table 14-150.","1) Change the name of the attribute to aOnuDynMacAgeLimit\n\n2) Change description to \"This attribute represents the age limit of the dynamic MAC addresses learned by the ONU.\"\n\n3) Change the name of this attribute in Table 14-150 to match the name in (1) - aOnuDynMacAgeLimit.\n\nImpact : Removing ambiguity (of whether this attribute is ONU context or UNI context) would actually reduce the risk of interoperability issues for this attribute in future implementations.  If interoperability issues are brought to light by this change, the interoperability issues already existed.\n","Edwin Mallette","Bright House Networks","edwin.mallette@bhnis.com","1.813.765.4527"]
["20131001_1523","Maintenance","New","None","None",null,"Technical","No",572,14,"14.4.3.2.2",null,"The attribute OnuDynMacAgeLimit when set to 0x00-00 is expected to disable the MAC address learning function in the ONU. it is not described in text right now. ","Change the value of the field in Table 14-150 from \"Value of aUniDynMacAgeLimit attribute\" to \"Value of aUniDynMacAgeLimit attribute:<cr>\n0x00-00: MAC learning function is disabled\n0x00-01 - 0xFF-FF: MAC learning function is enabled; the value expresses the MAC aging limit\"\n\nImpact = It is expected that backward compatibility with devices not implementing this specific meaning of this attribute might be affected. However, it is not clear how a device would implement really aging time of 0x00-00 and what it would mean. I expect that all devices in field today implement this specific meaning of OnuDynMacAgeLimit attribute anyway ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20131028_1808","Maintenance","New","None","None",null,"Technical","No",100,7,"7.2.2.3.2",null,"Footnote after Table 7-26 refers to parameter CVID. This parameter is not used in this table.","Delete table footnote 'b'.\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131029_1956","Maintenance","New","None","None",null,"Technical","No",581,14,"14.4.3.2.14",null,"Attribute aOnuFwFileName  (0xD7/0x01-0E) is located in the wrong section. It is located in the \"bridging\" subclause, while it should be located in the \"ONU management\" subclause.","Move 14.4.3.2.14 Attribute aOnuFwFileName (0xD7/0x01-0E) to 14.4.3.1.17 \n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131105_2020","Maintenance","New","None","None",null,"Technical","No",578,14,"14.4.3.2.11",null,"In 1904.1, the attribute aUniFloodUnknown is associated with a UNI port. But the same attribute in DPoE 2.0 is associated with an ONU, i.e., it enables/disables flooding on all UNI ports at once.","Controlling flooding per UNI is more flexible, so perhaps this is the method we should adopt in both standards. Otherwise, use ONU object in SIEPON.\n\nImpact = potential impact on ONU OAM parser","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131107_1410","Maintenance","New","None","None",null,"Technical","No",344,12,"12.3.3.1.4",1,"In the following sentence, the word \"potential\" is inappropriate. The message is sent only if actual errors were detected.\n\n\"In the case of any errors detected during the process of committing the newly downloaded software image, the ONU sends the eOAM_Software_FileTransferAck eOAMPDU with BlockNumber = 0x00-00 and ResponseCode field that holds any of the values specified in Table 13-101, indicating a potential problem with the software image committing step.\"","Remove the word \"potential\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131107_1416","Maintenance","New","None","None",null,"Technical","No",344,12,"12.3.3.2.1",null,"Typo in the definition of \"retryLimit\" variable. In the following sentence, the \"retryCountMax\" should be replaced with \"retryLimit\":\n\n\"Once the retryCountMax transmission attempts fail, the given device reacts per Figure 12-21 for the ONU and Figure 12-22 for the OLT.\"","replace \"retryCountMax\" with \"retryLimit\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131107_1440","Maintenance","New","None","None",null,"Technical","No",345,12,"12.3.3.2.2",null,"\"This bit array carries the software image fragment (block) carried in the eOAM_Software_FileTransferData eOAMPDU.\"\n\n\"carries\" and \"carried\" in the same sentence. Generally message carries information, but bit array (as any data types) just contains it.","Replace the sentence to read \"This bit array contains the software image fragment (block) carried in the eOAM_Software_FileTransferData eOAMPDU.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131107_1442","Maintenance","New","None","None",null,"Technical","No",347,12,"12.3.3.2.4",null,"\"This function extracts the software image block number block# from the software image pointed to by image and returns in the form of a bit array saved into the blockData variable.\"\n\nMissing \"it\" after \"returns\".","Insert \"it\" after \"returns\".\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131107_1448","Maintenance","New","None","None",null,"Technical","No",353,12,"12.3.3.2.6",null,"Two typos in figure 12-22: \n“eOAM_FTA_Error” in state TRANSFER_ERROR should be “eOAMI_FTA_Error” \n“eOAM_FTA_Error” in state COMMIT_ERROR should be “eOAMI_FTA_ErrorCommit”","In state TRANSFER_ERROR, replace “eOAM_FTA_Error”  with “eOAMI_FTA_Error” \nIn state COMMIT_ERROR, replace “eOAM_FTA_Error” with “eOAMI_FTA_ErrorCommit”\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20140807_2103","Maintenance","New","None","None",null,"Technical","No",400,13,"13.2.3.5",2,"eOAM_Set_Response eOAMPDU is used by ONU to respond to the eOAM_Set_Request eOAMPDU and contains a series of Variable Containers and Object_ID TLVs.","Change eOAM_Get_Request eOAMPDU in this line to eOAM_Set_Request eOAMPDU.\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20140807_2104","Maintenance","New","None","None",null,"Technical","No",518,14,"14.2.2.29",18,"When the OLT uses the Fast-Leave Admin Control TLV (0xC9/0x00-48) to configure the ONU IGMP/MLD agent, ‘enable’ is expressed by 0x00-00-00-02. While in this TLV, the status ‘enable’ is expressed by 0x00-00-00-00. We should keep the value consistent.","In Table 14-45, change enable: 0x00-00-00-00 to enable: 0x00-00-00-02\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20140807_2105","Maintenance","New","None","None",null,"Technical","No",545,14,"14.2.5.3",17,"This TLV is used by OLT to configures the fast-leave state function of the ONU, i.e., enable or disable the fast leave function. And it does not relate to the multicast mode. Furthermore, this is an action which means the attribute is write-only, so it can not represent the current state of the multicast mode.","Delete the paragraph: ‘The state of the fast-leave mode carried in this TLV represents the current state of enabled multicast mode of the ONU, e.g., IGMP-controlled multicast without authorization control mode or IGMP-controlled multicast with authorization control mode.’\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20140807_2106","Maintenance","New","None","None",null,"Technical","No",353,12,"12.3.1.6.2",2,"The message used by OLT instructing the ONU verify the downloaded software image is eOAM_Software_EndDownloadRequest eOAMPDU.","Change eOAM_Software_EndTransferRequest eOAMPDU to eOAM_Software_EndDownloadRequest eOAMPDU.\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20140807_2106a","Maintenance","New","None","None",null,"Technical","No",350,12,"12.3.1.6.2",23,"The message used by OLT instructing the ONU verify the downloaded software image is eOAM_Software_EndDownloadRequest eOAMPDU.","Change eOAM_Software_EndTransferRequest eOAMPDU to eOAM_Software_EndDownloadRequest eOAMPDU.\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20140807_2107","Maintenance","New","None","None",null,"Technical","No",351,12,"12.3.1.6.2",8,"The message used by OLT instructing the ONU verify the downloaded software image is eOAM_Software_EndDownloadRequest eOAMPDU","Change eOAM_Software_EndTransferRequest eOAMPDU to eOAM_Software_EndDownloadRequest eOAMPDU.\n\nImpact = None","Lu Yang","RITT, CATR","luyang@ritt.cn","+86-10-62300117"]
["20131107_1456","Maintenance","New","None","None",null,"Technical","No",436,13,"13.4.2.10.4",null,"Wrong description of the BlockNumber field in Table 13-100. \n\n\"This field reflects the sequential number of the current ONU software image fragment carried in this eOAMPDU.\"\n\nThe eOAM_Software_FileTransferAck eOAMPDU does not carry any software image fragments. ","Replace the sentence \n\n\"This field reflects the sequential number of the current ONU software image fragment carried in this eOAMPDU.\"\n\nwith the sentence\n\n\"“This field carries the sequential number of the software image fragment (block) that the ONU expects to receive next.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131108_2017","Maintenance","New","None","None",null,"Technical","No",118,7,"7.4.2.1",null,"\"The OLT handles the IGMP/MLD of the network, and the ONU filters the multicast data stream as instructed by the OLT through eOAM.\"\n\nThe sentence is confusing.","Rephrase as follows:\n\n\"The OLT handles all IGMP/MLD requests form the multicast clients on the given EPON, and the ONU filters the multicast data stream as instructed by the OLT through eOAM.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131108_2025","Maintenance","New","None","None",null,"Technical","No",289,11,"11.3.4.1.2",null,"In table 11-2, the following sentence is poorly worded and is confusing. \n\n\"This rule is added to all rules that direct to iU referring to LLIDU.\"\n\nIt is incorrect to say that a rule is added to another rule.","Rephrase as follows:\n\n\"This rule is added to precede all rules that direct data traffic to iU associated with the unauthenticated LLIDU.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131108_2037","Maintenance","New","None","None",null,"Technical","No",473,14,"14.2.2.22",null,"The following sentence is confusing. \n\n\"The OLT shall place the length of the IPv6 prefix in the lower octet of the sRuleFieldValue sub-attribute and the value of the prefix starting from  the higher octet of the sRuleFieldValue sub-attribute.\"","Rephrase as follows:\n\n\"The OLT shall place the length of the IPv6 prefix in the lowest octet of the sRuleFieldValue sub-attribute and it shall place the value of the prefix in the higher octets of the sRuleFieldValue sub-attribute, starting from the highest octet.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131108_2040","Maintenance","New","None","None",null,"Technical","No",510,14,"14.2.5.1",null,"The following sentence is confusing. \n\n\"The ONU may not respond to the eOAM_Set_Request eOAMPDU carrying this TLV with the eOAM_Set_Response eOAMPDU with the appropriate return code.\"\n\n“may not” can be interpreted as “not allowed”. Also not clear: no response from the ONU or a response, but with an incorrect code?","Rephrase as follows:\n\n\"The ONU may reboot without generating the eOAM_Set_Response eOAMPDU in  response to the eOAM_Set_Request eOAMPDU carrying the ONU Reboot TLV.\"\n\nImpact = None","Glen Kramer","Broadcom","gkramer@broadcom.com","707-529-0917"]
["20131111_0631","Maintenance","New","None","None",null,"Technical","No",306,12,"12.2.2.2 ",14,"A field name in the OAMPDU should be a single word by using \"_\" (underscore) to avoid confusion to readers.\nSee also the comment #22206 for IEEE P1904.1/Conformance resolved in the IEEE P1904.1 Working Group.","Change \"Vendor Specific Information\" and \"Vendor Specific Info\" to \"Vendor_Specific_Information\" in 12.2.2.2, Figure 12-7 and Table 12-2.\nImpact = None","Motoyuki Takizawa","Fujitsu Telecom Networks","takizawa.motoyu@jp.fujitsu.com","81-44-814-9032"]
["20140103_1828","Maintenance","New","None","None",null,"Technical","No",325,12,"12.3.1.6.5",null,"The value of EventID for eOAMR_ActivationFailure and eOAMR_ActivationSuccess is not correct.\neOAMR_ActivationFailure uses now EventID of 0x00-0E and eOAMR_ActivationSuccess - 0x00-0F. However, the normative Table 9-2 assigns EventID of 0x00-0E to ActivationSuccessEvent and 0x00-0F to ActivationFailureEvent. ","Change the value of EventID in definition of eOAMR_ActivationFailure from 0x00-0E to 0x00-0F. \nChange the value of EventID in definition of eOAMR_ActivationSuccess from 0x00-0F to 0x00-0E.\n\nImpact = None","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
["20140212_1524","Maintenance","New","None","None",null,"Technical","No",null,13,"13.4.4",null,"AI from comment #23185 called for an MR on Package A OAM definitions, adding text around the requirement to respond within 1 second, as discussed at December 2013 meeting. ","See siepon_1402_hajduczenia_1a for details of changes - two new subclauses are added: one in Clause 13, and one in Clause 14. \n\nImpact = None, it is just formal description of already existing behaviour. ","Marek Hajduczenia","Bright House Networks","marek.hajduczenia@ieee.org","1.813.465.0669"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K198)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K199)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K200)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K201)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K202)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K203)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K204)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K205)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K206)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K207)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K208)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K209)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K210)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K211)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K212)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K213)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K214)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K215)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K216)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K217)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K218)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K219)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K220)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K221)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K222)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K223)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K224)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K225)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K226)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K227)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K228)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K229)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K230)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K231)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K232)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K233)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K234)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K235)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K236)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K237)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K238)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K239)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K240)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K241)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K242)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K243)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K244)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K245)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K246)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K247)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K248)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K249)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K250)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K251)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K252)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K253)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K254)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K255)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K256)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K257)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K258)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K259)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K260)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K261)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K262)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K263)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K264)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K265)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K266)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K267)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K268)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K269)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K270)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K271)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K272)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K273)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K274)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K275)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K276)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K277)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K278)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K279)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K280)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K281)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K282)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K283)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K284)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K285)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K286)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K287)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K288)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K289)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K290)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K291)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K292)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K293)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K294)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K295)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K296)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K297)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K298)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K299)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K300)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K301)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K302)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K303)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K304)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K305)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K306)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K307)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K308)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K309)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K310)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K311)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K312)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K313)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K314)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K315)","v":""}]
[null,null,null,null,null,null,null,null,null,{"$f":"get_Clause_assignment(K316)","v":""}]

{"sheet":"Stats","index":1,"n_rows":22,"n_cols":7,"rows_kept":22,"cut":false,"hidden":false,"merged":[]}
[null,"E","ER","T","TR",null,"Totals"]
[0,{"$f":"get_Stats($A2,B$1)","v":0},0,0,0,null,{"$f":"SUM(B2:F2)","v":0}]
[99,0,0,0,0,null,{"$f":"SUM(B3:F3)","v":0}]
[1,0,0,0,0,null,{"$f":"SUM(B4:E4)","v":0}]
[2,0,0,1,0,null,1]
[3,0,0,0,0,null,0]
[4,0,0,0,0,null,0]
[5,0,0,0,0,null,0]
[6,0,0,1,0,null,1]
[7,0,0,4,0,null,4]
[8,0,0,2,0,null,2]
[null,null,null,null,null,null,{"$f":"SUM(G2:G11)","v":8}]
["Totals",{"$f":"SUM(B2:B11)","v":0},{"$f":"SUM(C2:C11)","v":0},{"$f":"SUM(D2:D11)","v":8},{"$f":"SUM(E2:E11)","v":0},{"$f":"SUM(B13:E13)","v":8},{"$f":"IF(F13=G12,\"OK\",\"ERROR\")","v":"OK"}]
[]
["TFs","Conformance1","Conformance2","Conformance3"]
["All",{"$f":"SUM(G2:G7,G8:G8)","v":1},{"$f":"SUM(G9:G10)","v":5},{"$f":"SUM(G11)","v":2}]
["E",{"$f":"SUM(B2:B7,B8:B8)","v":0},{"$f":"SUM(B9:B10)","v":0},{"$f":"SUM(B11)","v":0}]
["ER",{"$f":"SUM(C2:C7,C8:C8)","v":0},{"$f":"SUM(C9:C10)","v":0},{"$f":"SUM(C11)","v":0}]
["T",{"$f":"SUM(D2:D7,D8:D8)","v":1},{"$f":"SUM(D9:D10)","v":5},{"$f":"SUM(D11)","v":2}]
["TR",{"$f":"SUM(E2:E7,E8:E8)","v":0},{"$f":"SUM(E9:E10)","v":0},{"$f":"SUM(E11)","v":0}]
["E+ER",{"$f":"SUM(B17:B18)","v":0},{"$f":"SUM(C17:C18)","v":0},0]
["T+TR",{"$f":"SUM(B19:B20)","v":1},{"$f":"SUM(C19:C20)","v":5},2]

{"sheet":"Status change flow","index":3,"n_rows":6,"n_cols":2,"rows_kept":6,"cut":false,"hidden":false,"merged":[[1,0,1,1]]}
[]
["Legend"]
[]
["CS","Comment Status"]
["CC","Commenter Satisfaction"]
["RS","Response Status"]

{"sheet":"Tools","index":4,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["Sponsor Ballot Tools"]

{"sheet":"Parameters","index":5,"n_rows":50,"n_cols":8,"rows_kept":50,"cut":false,"hidden":true,"merged":[]}
[10000,"TF1","New","AIP","Satisfied","Technical","Yes",50]
[null,"TF2","Incomplete","Accept","Unsatisfied","Editorial","No",49]
[null,"TF3","Postponed","Reject",null,null,null,48]
[null,"TF4","Resolved",null,null,null,null,47]
[null,"WG","Withdrawn",null,null,null,null,46]
[null,null,"Proposed",null,null,null,null,45]
[null,null,"Closed",null,null,null,null,44]
[null,null,null,null,null,null,null,43]
[null,null,null,null,null,null,null,42]
[null,null,null,null,null,null,null,41]
[null,null,null,null,null,null,null,40]
[null,null,null,null,null,null,null,39]
[null,null,null,null,null,null,null,38]
[null,null,null,null,null,null,null,37]
[null,null,null,null,null,null,null,36]
[null,null,null,null,null,null,null,35]
[null,null,null,null,null,null,null,34]
[null,null,null,null,null,null,null,33]
[null,null,null,null,null,null,null,32]
[null,null,null,null,null,null,null,31]
[null,null,null,null,null,null,null,30]
[null,null,null,null,null,null,null,29]
[null,null,null,null,null,null,null,28]
[null,null,null,null,null,null,null,27]
[null,null,null,null,null,null,null,26]
[null,null,null,null,null,null,null,25]
[null,null,null,null,null,null,null,24]
[null,null,null,null,null,null,null,23]
[null,null,null,null,null,null,null,22]
[null,null,null,null,null,null,null,21]
[null,null,null,null,null,null,null,20]
[null,null,null,null,null,null,null,19]
[null,null,null,null,null,null,null,18]
[null,null,null,null,null,null,null,17]
[null,null,null,null,null,null,null,16]
[null,null,null,null,null,null,null,15]
[null,null,null,null,null,null,null,14]
[null,null,null,null,null,null,null,13]
[null,null,null,null,null,null,null,12]
[null,null,null,null,null,null,null,11]
[null,null,null,null,null,null,null,10]
[null,null,null,null,null,null,null,9]
[null,null,null,null,null,null,null,8]
[null,null,null,null,null,null,null,7]
[null,null,null,null,null,null,null,6]
[null,null,null,null,null,null,null,5]
[null,null,null,null,null,null,null,4]
[null,null,null,null,null,null,null,3]
[null,null,null,null,null,null,null,2]
[null,null,null,null,null,null,null,1]

{"sheet":"Values","index":6,"n_rows":25,"n_cols":7,"rows_kept":25,"cut":false,"hidden":true,"merged":[]}
["None","None","WG","None","Technical","Yes",0]
["New","AIP","TF1","Satisfied","Editorial","No",1]
["Proposed","Accept","TF2","Unsatisfied",null,null,2]
["Postponed","Reject","TF3","TBD",null,null,3]
["Incomplete",null,"TF4",null,null,null,4]
["Withdrawn",null,"TF5",null,null,null,"4A"]
["Resolved",null,null,null,null,null,"4B"]
[null,null,null,null,null,null,"4C"]
[null,null,null,null,null,null,5]
[null,null,null,null,null,null,"5A"]
[null,null,null,null,null,null,6]
[null,null,null,null,null,null,7]
[null,null,null,null,null,null,"7A"]
[null,null,null,null,null,null,8]
[null,null,null,null,null,null,9]
[null,null,null,null,null,null,"9A"]
[null,null,null,null,null,null,"9B"]
[null,null,null,null,null,null,10]
[null,null,null,null,null,null,"10A"]
[null,null,null,null,null,null,11]
[null,null,null,null,null,null,12]
[null,null,null,null,null,null,13]
[null,null,null,null,null,null,"13A"]
[null,null,null,null,null,null,14]
[null,null,null,null,null,null,99]