## IEEEcover
October 2002 |  | IEEE P802.15-02/406r9
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 LB19 comment drafting status
Date Submitted | [October 2, 2002]
Source | [James P. K. Gilb] | Voice: [(858)-538-3903]
| [Appairent Technologies] | Fax: [(858)-538-3903 ]
| [9921 Carmel Mountain Rd., #247] | E-mail: [gilb@ieee.org ]
[San Diego, CA 92129]
Re: | [00000D10P802.15.3-Draft-Standard]
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comment resolution and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | Left to go | 11
|  | Total finished | 540
|  | Left to claim | 0 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Singer | AS comments | Sarallo | JS comments | Schrader | MKS comments | Bain | JB comments | Tally | Claimed
1 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
2 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
3 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
4 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
5 | Done |  |  | Done | Checked for Time token, defined beacon number in 7.3.1 |  | Check Time Token usage. Everything else is done. | [5 empty] | done my part | 1 | 0
6 | done | done | SEC T | [10 empty] | 1 | 0
7 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
8 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
9 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
10 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
11 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
12 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
13 | done | done | PNCInfo TR | [10 empty] | 1 | 0
14 | done | done | PM/SPS TR | [10 empty] | 1 | 0
15 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
16 | done | done | PM/SPS TR need a defn for awake beacon fo clause 7.5.7.3 | [10 empty] | 1 | 0
17 | Done | [6 empty] | Done | [5 empty] | 1 | 0
18 | Done | [6 empty] | Done | [5 empty] | 1 | 0
19 | Done | [6 empty] | Done | [5 empty] | 1 | 0
20 | Done | [6 empty] | Done | [5 empty] | 1 | 0
21 | done | done | Handover TR | [10 empty] | 1 | 0
22 | done | done | CTM TR Contains Ed note for 8.5.2.1 . | [10 empty] | 1 | 0
23 | Done |  |  | Done | Changed table entries in clause 7. | [7 empty] | moved to Allen | 1 | 0
24 | Done | [6 empty] | Done | [5 empty] | 1 | 0
25 | Done | [6 empty] | Done | [5 empty] | 1 | 0
26 | Done | [6 empty] | Done | [5 empty] | 1 | 0
27 | Done | [6 empty] | Done | [5 empty] | 1 | 0
28 | Done | [6 empty] | Done | [5 empty] | 1 | 0
29 | Done | [6 empty] | Done | [5 empty] | 1 | 0
30 | Done | [6 empty] | Done | [5 empty] | 1 | 0
31 | Done | [6 empty] | Done | [5 empty] | 1 | 0
32 | Done | [6 empty] | Done | Jay confirmed done |  |  |  | from clause 6 | 1 | 0
33 | Done |  |  | Done | Verified that edits were made, part of 8.6.4 remains, the rest is in disassociation. | [7 empty] | merge of 8.6.4 and 8.6.3 + multi-clause 6 remain | 1 | 0
34 | Done | [6 empty] | Done | [5 empty] | 1 | 0
35 | Done | [6 empty] | Done | [5 empty] | 1 | 0
36 | Done | [6 empty] | Done | [5 empty] | 1 | 0
37 | done | [10 empty] | done | multi-location - clause 6 and fig 96 | 1 | 0
38 | done | done | Beacon TR same resolution as CID 405 Beacon | [10 empty] | 1 | 0
39 | Done | [6 empty] | Done | [5 empty] | 1 | 0
40 | done | done | Handover TR | [10 empty] | 1 | 0
41 | done | done | Handover TR | [10 empty] | 1 | 0
42 | done |  |  |  | Reviewed MSC, should be fine. | [6 empty] | done | text done, fig 91 requires review | 1 | 0
43 | done | done | Beacon TR same resolution as in CID 413 Beacon | [10 empty] | 1 | 0
44 | Done | [6 empty] | Done | [5 empty] | 1 | 0
45 | done | done | RemoteScan TR | [10 empty] | 1 | 0
46 | done | [10 empty] | done |  | 1 | 0
47 | done | [10 empty] | done | fig 127 & 128 change | 1 | 0
48 | Done | [6 empty] | Done | [5 empty] | 1 | 0
49 | Done | [6 empty] | Done | [5 empty] | 1 | 0
50 | done | [10 empty] | done | multi-location - clause 6 | 1 | 0
51 | Done |  |  | Done | New async figure with input from ADH added | [7 empty] | same as 265 - fig 116 | 1 | 0
52 | Done |  |  | Done | Added the table from 02/392, deleted DEV address and added CTA status request and CTA status | [7 empty] | sent to allen - probe table | 1 | 0
53 | done | [10 empty] | done |  | 1 | 0
54 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
55 | done | [10 empty] | done | same as 293 | 1 | 0
56 | Done |  |  | Done | MTS resolution | [8 empty] | 1 | 0
57 | Done | [6 empty] | Done | [5 empty] | 1 | 0
58 | Done |  |  | Done | Primitive added to MSC by others | [8 empty] | 1 | 0
59 | Done |  |  | Done | Applied xref to clause 8, added text to clause 11.2.9 | [7 empty] | waiting for James | 1 | 0
60 | Done |  |  | Done | New text is in clause 11 | [7 empty] | waiting for james - 11 | 1 | 0
61 | done | [10 empty] | done | withdrawn | 1 | 0
62 | Done |  |  | Done | PICS | [8 empty] | 1 | 0
63 | Done |  |  | Done | Verified that the edit was made to clause 7 |  | Applies to page 130. Needs to be completed by Allen. After the simple change is made, this is done. | [6 empty] | 1 | 0
64 | Done |  |  | Done | Verified that the references were added. |  | Need to confirm that references are added appropriately. Otherwise done. | [6 empty] | 1 | 0
65 | done | [10 empty] | done | same as cid 262 resolved - PM | 1 | 0
66 | Done |  |  | Done | Edit to A.1.2 | [8 empty] | 1 | 0
67 | done | [10 empty] | done |  | 1 | 0
68 | Done |  |  | Done | Applied xref to clause 8, added text to clause 11.2.9 | [7 empty] | same as cid 59 - waiting for james | 1 | 0
69 | done | [10 empty] | done | multi-location- clause 11 | 1 | 0
70 | done | [10 empty] | done |  | 1 | 0
71 | done | done | CTM TR | [9 empty] | my part done | 1 | 0
72 | Done |  |  | Done | [9 empty] | 1 | 0
73 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
74 | done | [10 empty] | done | multi-location -11 | 1 | 0
75 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
76 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
77 | Done |  |  | Done | [9 empty] | 1 | 0
78 | Done |  |  | Done | [9 empty] | 1 | 0
79 | Done |  |  | Done | [9 empty] | 1 | 0
80 | Done | [6 empty] | Done | [5 empty] | 1 | 0
81 | Done | [6 empty] | Done | Added parms to indication as well. |  |  |  |  | 1 | 0
82 | Done | [6 empty] | Done | Marked REJECTED. |  |  |  |  | 1 | 0
83 | Done |  |  | Done | Verified that figure 146 was updated |  |  |  | Clause 6 changes done, Ari to change figure 146 |  |  |  |  | 1 | 0
84 | Done | [6 empty] | Done | Withdrawn, 12 September, 2002 |  |  |  |  | 1 | 0
85 | Done | [6 empty] | Done | Ari provided definition for "Key" |  |  |  |  | 1 | 0
86 | Done | [6 empty] | Done | [5 empty] | 1 | 0
87 | Done | [6 empty] | Done | [5 empty] | 1 | 0
88 | Done | [6 empty] | Done | [5 empty] | 1 | 0
89 | Done | [6 empty] | Done | [5 empty] | 1 | 0
90 | Done | [6 empty] | Done | [5 empty] | 1 | 0
91 | Done |  |  | Done | See CID 102 commnet |  | Resolved when CID 102 is resolved. | [6 empty] | 1 | 0
92 | Done |  |  | Done | JPKG checked for all instances of mode |  | Need to confirm clause 6 changes. Otherwise done. | [5 empty] | I need to check for mode 2 | 1 | 0
93 | Done |  |  |  |  | Done |  |  | Ari confirmed no Clause 6 work |  |  |  |  | 1 | 0
94 | done | done | bitorder T | [10 empty] | 1 | 0
95 | done | done | FrmFmt T | [10 empty] | 1 | 0
96 | done | done | FrmFmt TR | [10 empty] | 1 | 0
97 | done | done | FrmFmt TR | [10 empty] | 1 | 0
98 | Done |  |  | Done | ADH made the change, but forgot to not it here. | [8 empty] | 1 | 0
99 | done | done | SEC TR resolved in CID 6 SEC | [10 empty] | 1 | 0
100 | Done | [6 empty] | Done | [5 empty] | 1 | 0
101 | done | done | SEC TR |  |  |  | All edits applied (JPKG checked) | [6 empty] | 1 | 0
102 | Done |  | SEC/Handover TR need text from 02/399r1 | Done | Confirmation from ADH, JCS and AS that edits were applied. | [8 empty] | 1 | 0
103 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
104 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
105 | Done |  |  | Done | Xref added by JPKG |  | Done except for the cross reference to the new command. | [6 empty] | 1 | 0
106 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
107 | Done | [6 empty] | Done | [5 empty] | 1 | 0
108 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
109 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
110 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
111 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
112 | Done |  |  |  |  | Done | No resolution in databse, but fixed as 93. | [6 empty] | 1 | 0
113 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
114 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
115 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
116 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
117 | Done |  |  | Done | The rest will be fixed as editorial as time permits. |  | Not planning on doing any more on this. Rene just sent out some text yesterday. | [6 empty] | 1 | 0
118 | Done |  |  |  |  | Done | Rejected | [6 empty] | 1 | 0
119 | Done |  |  |  |  | Done | Changes should be approved by other security members. | [6 empty] | 1 | 0
120 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
121 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
122 | Done |  |  |  |  | Done | Exact change not specified in database, but taken from my document. | [6 empty] | 1 | 0
123 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
124 | Done |  |  | Done | Added xrefs to PICs, updated to match the text | [8 empty] | 1 | 0
125 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
126 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
127 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
128 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
129 | Done | [6 empty] | Done | [5 empty] | 1 | 0
130 | Done | [6 empty] | Done | [5 empty] | 1 | 0
131 | Done | [6 empty] | Done | [5 empty] | 1 | 0
132 | Done | [6 empty] | Done | [5 empty] | 1 | 0
133 | Done | [6 empty] | Done | Changed indication as well |  |  |  |  | 1 | 0
134 | Done | [6 empty] | Done | Removed ChannelIndex |  |  |  |  | 1 | 0
135 | Done | [6 empty] | Done | Should be Accept in Principle because exact definition for parameter not used based on 133 |  |  |  |  | 1 | 0
136 | Done | [6 empty] | Done | [5 empty] | 1 | 0
137 | Done | [6 empty] | Done | [5 empty] | 1 | 0
138 | Done | [6 empty] | Done | [5 empty] | 1 | 0
139 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
140 | Done | [6 empty] | Done | [5 empty] | 1 | 0
141 | Done | [6 empty] | Done | [5 empty] | 1 | 0
142 | Done | [6 empty] | Done | [5 empty] | 1 | 0
143 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
144 | Done | [6 empty] | Done | [5 empty] | 1 | 0
145 | Done | [6 empty] | Done | [5 empty] | 1 | 0
146 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
147 | Done | [6 empty] | Done | Jay confirmed done |  |  |  | multi with clause 6 | 1 | 0
148 | Done | [6 empty] | Done | [5 empty] | 1 | 0
149 | Done | [6 empty] | Done | [5 empty] | 1 | 0
150 | Done | [6 empty] | Done | [5 empty] | 1 | 0
151 | Done | [6 empty] | Done | [5 empty] | 1 | 0
152 | Done | [6 empty] | Done | [5 empty] | 1 | 0
153 | Done | [6 empty] | Done | [5 empty] | 1 | 0
154 | Done | [6 empty] | Done | [5 empty] | 1 | 0
155 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
156 | Done | [6 empty] | Done | What about modify? |  |  |  |  | 1 | 0
157 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
158 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
159 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
160 | Done | [6 empty] | Done | [5 empty] | 1 | 0
161 | Done | [6 empty] | Done | [5 empty] | 1 | 0
162 | Done | [6 empty] | Done | [5 empty] | 1 | 0
163 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
164 | Done | [6 empty] | Done | [5 empty] | 1 | 0
165 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
166 | Done | [6 empty] | Done | [5 empty] | 1 | 0
167 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
168 | Done | [6 empty] | Done | [5 empty] | 1 | 0
169 | Done | [6 empty] | Done | [5 empty] | 1 | 0
170 | done | [10 empty] | done |  | 1 | 0
171 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
172 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
173 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
174 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
175 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
176 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
177 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
178 | Done | [6 empty] | Done | [5 empty] | 1 | 0
179 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
180 | Done | [6 empty] | Done | [5 empty] | 1 | 0
181 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
182 | Done | [6 empty] | Done | [5 empty] | 1 | 0
183 | done | done | FrmFmt TR resolved by CID 97 FrmFmt | [10 empty] | 1 | 0
184 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
185 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
186 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
187 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
188 | Done |  |  | Done | Editorial, changes handled by CID 97 | [8 empty] | 1 | 0
189 | done | done | FrmFmt T | [10 empty] | 1 | 0
190 | Done |  |  | Done | Editorial, changes handled by CID 97 | [8 empty] | 1 | 0
191 | done | done | FrmFmt T | [10 empty] | 1 | 0
192 | done | done | Bitorder TR | [10 empty] | 1 | 0
193 | done | done | MaxCTA TR resolved by CID 201 MaxCTA | [10 empty] | 1 | 0
194 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
195 | done | done | ASIE TR | [9 empty] | done for clause 7 | 1 | 0
196 | done | done | FrmFmt TR see CID 359 Pm/PSPS for suggested resolution. Dbl chk w/ KO. | [10 empty] | 1 | 0
197 | done | done | MaxCTA TR resolved by CID 201 MaxCTA | [10 empty] | 1 | 0
198 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
199 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
200 | done | done | PNID TR | [10 empty] | 1 | 0
201 | done | done | MaxCTA TR | [9 empty] | did figure 115 | 1 | 0
202 | done | done | PNID TR | [10 empty] | 1 | 0
203 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
204 | done | done | PNID TR | [10 empty] | 1 | 0
205 | done | done | PNID TR | [10 empty] | 1 | 0
206 | done | done | MaxCTA TR resolved by CID 201 MaxCTA | [10 empty] | 1 | 0
207 | done | done | PNID TR | [10 empty] | 1 | 0
208 | done | done | CTM TR resolved by CID 301 CTM | [9 empty] | CTA status command to IE | 1 | 0
209 | done | done | PNID TR | [10 empty] | 1 | 0
210 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
211 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
212 | Done | [6 empty] | Done | [5 empty] | 1 | 0
213 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
214 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
215 | done | done | ACK TR | [10 empty] | 1 | 0
216 | Done |  | RemoteScan TR Has text for clause 6.3.18. JS needs to integrate suggested text. | Done | Table added by JCS, change to RemotePiconetDescriptionsSet by JPKG | [8 empty] | 1 | 0
217 | done | done | Assoc TR | [10 empty] | 1 | 0
218 | done | [10 empty] | done |  | 1 | 0
219 | done | done | MaxCTA TR | [10 empty] | 1 | 0
220 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
221 | done | done | DepPN TR | [10 empty] | 1 | 0
222 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
223 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
224 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
225 | done | done | ParmChange TR | [10 empty] | 1 | 0
226 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
227 | done | done | IE TR | [10 empty] | 1 | 0
228 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
229 | done | done | MaxCTA TR resolved by CID 201 MaxCTA | [10 empty] | 1 | 0
230 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
231 | done | done | IE/Capabilities TR | [10 empty] | 1 | 0
232 | Done |  |  | Done | Added extra hexagon to figure | [7 empty] | fig from 392 inserted | 1 | 0
233 | done | done | ACK TR double chk w/ KO | [10 empty] | 1 | 0
234 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
235 | done | done | Handover | [10 empty] | 1 | 0
236 | Done |  |  | Done | Editorial, changes handled by CID 221 | [8 empty] | 1 | 0
237 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
238 | done | [10 empty] | done |  | 1 | 0
239 | done | done | SEC/Auth TR | [10 empty] | 1 | 0
240 | Done |  |  | Done | Editorial, changes handled by CID 221 | [7 empty] | editorial | 1 | 0
241 | done | done | SEC/Auth TR | [10 empty] | 1 | 0
242 | done | [10 empty] | done |  | 1 | 0
243 | done | done | Handover TR | [10 empty] | 1 | 0
244 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
245 | done | done | Handover TR | [10 empty] | 1 | 0
246 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
247 | done | done | Handover TR resolved by CID 249 Handover | [10 empty] | 1 | 0
248 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
249 | done | done | Handover TR | [10 empty] | 1 | 0
250 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
251 | Done |  |  | Done | Editorial, changes handled by CID 251 | [8 empty] | 1 | 0
252 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
253 | done | done | Handover TR | [10 empty] | 1 | 0
254 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
255 | done | done | PNServices TR | [10 empty] | 1 | 0
256 | Done |  | CTM TR need clarification from KO regarding MTS interval. Also need to reconcile the resolutions proposed in CID 293 MTS and CID 550 MTS | Done | JPKG added the extra sentence, verified that the others were done and cross checked with CIDs 293 and 550 | [8 empty] | 1 | 0
257 | done | [10 empty] | done |  | 1 | 0
258 | done | done | CTM/Asynch TR | [10 empty] | 1 | 0
259 | done | [10 empty] | done |  | 1 | 0
260 | done | done | DepPN TR | [10 empty] | 1 | 0
261 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
262 | Heberling | Heberling | PM/PSPS TR has text for clause 8.13.2.2 | [9 empty] | done for clause 7 | 0 | 0
263 | done | [10 empty] | done | fig 115 | 1 | 0
264 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
265 | Done |  |  | Done | New async figure with input from ADH added | [7 empty] | fig 116 as in cid 51 | 1 | 0
266 | done | done | PM TR | [10 empty] | 1 | 0
267 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
268 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
269 | done | [10 empty] | done | multi-clause content 6,7 | 1 | 0
270 | done | [10 empty] | done |  | 1 | 0
271 | done | [10 empty] | done | multi-clause go ahead and do it | 1 | 0
272 | done | [10 empty] | done |  | 1 | 0
273 | done | [10 empty] | done | used new PS proposal | 1 | 0
274 | done | [10 empty] | done |  | 1 | 0
275 | done | [10 empty] | done |  | 1 | 0
276 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
277 | done | [10 empty] | done | withdrawn | 1 | 0
278 | done | [10 empty] | done |  | 1 | 0
279 | done | [10 empty] | done |  | 1 | 0
280 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
281 | done | [10 empty] | done |  | 1 | 0
282 | done | [10 empty] | done | withdrawn | 1 | 0
283 | done | [10 empty] | done | reject | 1 | 0
284 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
285 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
286 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
287 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
288 | done | [10 empty] | done |  | 1 | 0
289 | done | [10 empty] | done |  | 1 | 0
290 | done | [10 empty] | done |  | 1 | 0
291 | done | [10 empty] | done | reject | 1 | 0
292 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
293 | done | [10 empty] | done |  | 1 | 0
294 | Done |  |  | Done | Added text as indicated in the database. | [8 empty] | 1 | 0
295 | done | done | SEC/Key TR | [10 empty] | 1 | 0
296 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
297 | done | [10 empty] | done |  | 1 | 0
298 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
299 | done | done | CTM TR resolved by CID 301 CTM | [10 empty] | 1 | 0
300 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
301 | done | done | CTM TR chk w/ KO as to whether it is CTR status or CTA status | [10 empty] | 1 | 0
302 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
303 | done | [10 empty] | done |  | 1 | 0
304 | done | [10 empty] | done | did fig part | 1 | 0
305 | done | [10 empty] | done |  | 1 | 0
306 | Done |  | RemoteScan TR Why are we redefining the Parent BSID to contain the parent's DEV address. | Done | Edits made according to resolution of this and other CIDs | [8 empty] | 1 | 0
307 | done | [10 empty] | done |  | 1 | 0
308 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
309 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
310 | done | [10 empty] | done |  | 1 | 0
311 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
312 | done | [10 empty] | done |  | 1 | 0
313 | done | [10 empty] | done | 2 dones - misplaced? | 1 | 0
314 | done | [10 empty] | done |  | 1 | 0
315 | done | [10 empty] | done |  | 1 | 0
316 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
317 | done | [10 empty] | done |  | 1 | 0
318 | done | done | Assoc T | [10 empty] | 1 | 0
319 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
320 | done | [10 empty] | done | includes fig 130 | 1 | 0
321 | jcb |  |  |  | Not resolved – PM | [6 empty] | jcb | need to add ps text | 0 | 0
322 | done | [10 empty] | done |  | 1 | 0
323 | Done |  |  | Done | [9 empty] | 1 | 0
324 | JPKG |  |  | JPKG | Not resolved – PM | [8 empty] | 0 | 0
325 | Done | [6 empty] | Done | Added parms to indication as well |  |  |  |  | 1 | 0
326 | Done | [6 empty] | Done | [5 empty] | 1 | 0
327 | Done | [6 empty] | Done | [5 empty] | 1 | 0
328 | Done | [6 empty] | Done | [5 empty] | 1 | 0
329 | Done | [6 empty] | Done | Withdrawn, 12 September, 2002 |  |  |  |  | 1 | 0
330 | Done | [6 empty] | Done | Withdrawn, 12 September, 2002 |  |  |  |  | 1 | 0
331 | done | done | ASIE TR | [9 empty] | done for clause 7 | 1 | 0
332 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
333 | Done |  |  | Done | Editorial, changes handled by CID 86 | [8 empty] | 1 | 0
334 | Done |  |  | Done | Editorial, changes handled by CID 86 | [8 empty] | 1 | 0
335 | done | done | PM/SPS TR | [10 empty] | 1 | 0
336 | done | done | PM/SPS TR | [10 empty] | 1 | 0
337 | done | [10 empty] | done | multi-clause content-- there is clause 8 content. (pg 189 d11) | 1 | 0
338 | done | [10 empty] | done |  | 1 | 0
339 | JPKG |  |  | JPKG | PM: PICS | [8 empty] | 0 | 0
340 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
341 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
342 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
343 | JPKG |  |  | JPKG | PM: PICS | [8 empty] | 0 | 0
344 | done | [10 empty] | done |  | 1 | 0
345 | done | done | bitorder TR resolved in CID 192 Bitorder | [10 empty] | 1 | 0
346 | done | done | PNServices TR | [10 empty] | 1 | 0
347 | done | done | ASIE TR | [9 empty] | done for clause 7 | 1 | 0
348 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
349 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
350 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
351 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
352 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
353 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
354 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
355 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
356 | Done |  |  | Done | Text updated to match 02/392r14 | [7 empty] | add PS text | 1 | 0
357 | done | [10 empty] | done |  | 1 | 0
358 | jcb |  |  |  | PM merge text | [6 empty] | jcb | add PS text | 0 | 0
359 | done | [10 empty] | done |  | 1 | 0
360 | Heberling | Heberling | PM TR awaiting resolution of this comment |  | PM merge text | [8 empty] | 0 | 0
361 | jcb |  |  |  | PM merge text | [6 empty] | jcb | add PS text | 0 | 0
362 | AS |  |  |  |  | AS | Editorial. Not done yet. May push off to next letter ballot. | [6 empty] | 0 | 0
363 | jcb |  |  |  | Not resolved – PM | [6 empty] | jcb | add PS text | 0 | 0
364 | JPKG |  |  | JPKG | PM: PICS | [8 empty] | 0 | 0
365 | done | [10 empty] | done |  | 1 | 0
366 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
367 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
368 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
369 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
370 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
371 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
372 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
373 | Done |  |  |  |  | Done | Withdrawn 12 September, 2002 | [6 empty] | 1 | 0
374 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
375 | Done |  |  |  |  | Done | BRC agreed on | [6 empty] | 1 | 0
376 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
377 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
378 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
379 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
380 | Done |  |  |  |  | Done | Withdrawn 12 September, 2002 | [6 empty] | 1 | 0
381 | Done |  |  |  |  | Done | Withdrawn 12 September, 2002 | [6 empty] | 1 | 0
382 | Done |  |  |  |  | Done | [7 empty] | 1 | 0
383 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
384 | Done | [6 empty] | Done | Ari confirmed. |  |  |  |  | 1 | 0
385 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
386 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
387 | Done |  |  | Done | [9 empty] | 1 | 0
388 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
389 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
390 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
391 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
392 | Done |  |  | Done | No changes, text was already in the draft | [8 empty] | 1 | 0
393 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
394 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
395 | Done |  |  | Done | Added text below the paragraphs | [8 empty] | 1 | 0
396 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
397 | done | done | SEC/Auth T | [10 empty] | 1 | 0
398 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
399 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
400 | done | done | CTM TR | [10 empty] | 1 | 0
401 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
402 | done | done | SEC T | [10 empty] | 1 | 0
403 | done | done | SEC T | [10 empty] | 1 | 0
404 | done | done | SEC T | [10 empty] | 1 | 0
405 | done | done | Beacon TR same resolution as CID 38 Beacon | [10 empty] | 1 | 0
406 | done | done | Beacon TR | [10 empty] | 1 | 0
407 | Done |  | MTS TR Text needs to be added to 11.2.10, and the PICs. James are you doing this? | Done | JPKG did edits for clause 11 and the PICS | [8 empty] | 1 | 0
408 | done | done | CAP T | [10 empty] | 1 | 0
409 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
410 | done | done | FrmFmt TR | [10 empty] | 1 | 0
411 | done | done | ACK T | [10 empty] | 1 | 0
412 | done | done | IE TR | [10 empty] | 1 | 0
413 | Done |  | Beacon TR need defns for PCTM, SPS, and PSPS I-Es | Done | This issues is handled with the table in the front of 7.4 now. | [8 empty] | 1 | 0
414 | done | done | Assoc TR | [10 empty] | 1 | 0
415 | done | done | Assoc TR resolved in 8.3.1, P164, L50-51 | [10 empty] | 1 | 0
416 | done | done | MaxCTA TR resolved by 201 and 219 MaxCTA | [10 empty] | 1 | 0
417 | done | done | Assoc T | [10 empty] | 1 | 0
418 | done | done | Assoc TR | [10 empty] | 1 | 0
419 | done | done | Assoc TR | [10 empty] | 1 | 0
420 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
421 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
422 | done | done | ParmChange TR | [10 empty] | 1 | 0
423 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
424 | Done |  | PNServices TR OUI acronym needs to be defined. James are you doing this? | Done | OUI added as acronym, ADH finished the rest of the comment. | [8 empty] | 1 | 0
425 | done | done | ASIE TR | [10 empty] | 1 | 0
426 | done | done | ASIE TR | [10 empty] | 1 | 0
427 | done | done | PM TR | [10 empty] | 1 | 0
428 | done | done | Handover T | [10 empty] | 1 | 0
429 | done | done | IE TR | [10 empty] | 1 | 0
430 | done | done | IE TR | [10 empty] | 1 | 0
431 | done | done | SEC TR | [10 empty] | 1 | 0
432 | done | done | SEC T | [10 empty] | 1 | 0
433 | done | done | BSID T | [10 empty] | 1 | 0
434 | done | done | PNServices TR | [10 empty] | 1 | 0
435 | done | done | Commands TR | [10 empty] | 1 | 0
436 | done | done | Frag TR | [10 empty] | 1 | 0
437 | done | done | ATP TR | [10 empty] | 1 | 0
438 | done | done | PNServices TR | [10 empty] | 1 | 0
439 | done | done | Assoc. TR | [10 empty] | 1 | 0
440 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
441 | done | done | Handover TR resolved by CID 41 Handover | [10 empty] | 1 | 0
442 | done | done | Handover TR | [10 empty] | 1 | 0
443 | done | done | Handover T | [10 empty] | 1 | 0
444 | Done |  |  | Done | Edits applied for other TRs | [8 empty] | 1 | 0
445 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
446 | done | done | PNServices same resolution as CID 434 PNServices | [10 empty] | 1 | 0
447 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
448 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
449 | done | done | CTM/Isoch T | [10 empty] | 1 | 0
450 | done | done | PM TR see CID 262 PM/PSPS | [10 empty] | 1 | 0
451 | done | done | ChnlStatus T | [10 empty] | 1 | 0
452 | Done |  | RemoteScan TR Why are we redefining the Parent BSID and the Piconet BSID I-Es to contain the parent's DEV address? | Done | This was decided in Monterrey to let DEVs know when the PNC changes | [8 empty] | 1 | 0
453 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
454 | Done |  |  | Done | Text added to 8.13 | [8 empty] | 1 | 0
455 | done | done | PM/SPS T | [10 empty] | 1 | 0
456 | done | done | Misc TR | [10 empty] | 1 | 0
457 | done | [10 empty] | done | rejected | 1 | 0
458 | Done | [6 empty] | Done | The resolution is handled by other CIDs, verify that stream index is added to the init-dependent-PNC primitive. |  |  |  |  | 1 | 0
459 | done | [10 empty] | done | same as 147 | 1 | 0
460 | done | [10 empty] | done | rejected | 1 | 0
461 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
462 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
463 | done | [10 empty] | done | done with 269 | 1 | 0
464 | done | [10 empty] | done | James will do editorial portion 10/8 | 1 | 0
465 | done | [10 empty] | done |  | 1 | 0
466 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
467 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
468 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
469 | done | [10 empty] | done |  | 1 | 0
470 | done | [10 empty] | done | change is in clause 7, cid 221 | 1 | 0
471 | done | [10 empty] | done | change is in clause 7, cid 221 | 1 | 0
472 | done | [10 empty] | done |  | 1 | 0
473 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
474 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
475 | done | [10 empty] | done |  | 1 | 0
476 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
477 | done | [10 empty] | done | rejected | 1 | 0
478 | done | [10 empty] | done | rejected | 1 | 0
479 | done | [10 empty] | done | rejected | 1 | 0
480 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
481 | Done |  |  | Done | Updates applied to clause 11 | [7 empty] | multi-clause content 11 | 1 | 0
482 | done | [10 empty] | done |  | 1 | 0
483 | Done |  |  | Done | change is in clause 3.2 | [7 empty] | change is in clause 3.2 | 1 | 0
484 | done | [10 empty] | done | 485 text is used | 1 | 0
485 | done | [10 empty] | done |  | 1 | 0
486 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
487 | done | [10 empty] | done |  | 1 | 0
488 | done | [10 empty] | done |  | 1 | 0
489 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
490 | done | [10 empty] | done |  | 1 | 0
491 | done | [10 empty] | done |  | 1 | 0
492 | done | [10 empty] | done | rejected | 1 | 0
493 | done | [10 empty] | done | no change required | 1 | 0
494 | done | [10 empty] | done |  | 1 | 0
495 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
496 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
497 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
498 | done | [10 empty] | done | rejected | 1 | 0
499 | done | [10 empty] | done |  | 1 | 0
500 | done | [10 empty] | done |  | 1 | 0
501 | done | [10 empty] | done | rejected | 1 | 0
502 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
503 | done | [10 empty] | done |  | 1 | 0
504 | done | [10 empty] | done |  | 1 | 0
505 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
506 | done | [10 empty] | done |  | 1 | 0
507 | done | [10 empty] | done | rejected | 1 | 0
508 | done | [10 empty] | done |  | 1 | 0
509 | done | [10 empty] | done | no change required | 1 | 0
510 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
511 | done | [10 empty] | done | cid 356 removed sentence | 1 | 0
512 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
513 | Done |  |  | Done | Add subclause to clause 11, bits added for other TRs | [8 empty] | 1 | 0
514 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
515 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
516 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
517 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
518 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
519 | Done |  |  | Done | Fixing them as I see them | [7 empty] | editorial | 1 | 0
520 | done | [10 empty] | done |  | 1 | 0
521 | Done |  |  | Done | [9 empty] | 1 | 0
522 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
523 | done | [10 empty] | done |  | 1 | 0
524 | Done |  |  | Done | Editorial | [7 empty] | figure change, 120 | 1 | 0
525 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
526 | done | [10 empty] | done |  | 1 | 0
527 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
528 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
529 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
530 | done | [10 empty] | done |  | 1 | 0
531 | done | done | Handover T resolved by CID 221 DepPN | [10 empty] | 1 | 0
532 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
533 | done | [10 empty] | done | as in 506 | 1 | 0
534 | done | done | PM/PSPS T resolved by CID 16 PM/SPS | [10 empty] | 1 | 0
535 | done | done | PM/PSPS T resolved by CID 16 PM/SPS | [10 empty] | 1 | 0
536 | done | done | IE T have questions regarding defn. of non-Beacon IE. It seems contradictory. | [10 empty] | 1 | 0
537 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
538 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
539 | Done |  |  | Done | Editorial | [7 empty] | editorial | 1 | 0
540 | done | [10 empty] | done |  | 1 | 0
541 | Done | [6 empty] | Done | [5 empty] | 1 | 0
542 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
543 | done | [10 empty] | done |  | 1 | 0
544 | Done | [6 empty] | Done | [5 empty] | 1 | 0
545 | Done | [6 empty] | Done | [5 empty] | 1 | 0
546 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
547 | done | [10 empty] | done |  | 1 | 0
548 | Done | [6 empty] | Done | [5 empty] | 1 | 0
549 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
550 | done | done | MTS T see also CID 256 CTM | [10 empty] | 1 | 0
551 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
Total assigned |  | 115 |  | 213 |  | 39 |  | 80 |  | 0 |  | 104 |  | 551
Total resolved |  | 113 |  | 209 |  | 38 |  | 80 |  | 0 |  | 100 |  | 540
Total left to finish |  | 2 |  | 4 |  | 1 |  | 0 |  | 0 |  | 4 |  | 11

## Commentsresolved
Total left to close | 11 |  | Assigned to others | 0 | Assigned to Gilb | 0 | Assigned to Odman | 0 | Assigned to Schrader/Bain | 0 | PM | 9 | Pmwake | 0 | Editorials for Gilb | 0
Total left to assign | 0 |  |  |  | Assigned to Singer | 2 | Assigned to Heberling | 0 | Assigned to Bain | 0 | MTS | 0 | MaxCTAs | 0 | T & TR's left | 11
Comment ID | Assigned to | Status | Due date | Not Assigned | Assgned to Schrader | 0 | Assigned to Sarallo | 0
1 | Closed |  |  | 0
2 | Closed |  |  | 0
3 | Closed |  |  | 0
4 | Closed |  |  | 0
5 | Closed | John, do you approve? |  | 0
6 | Closed |  |  | 0
7 | Closed |  |  | 0
8 | Closed |  |  | 0
9 | Closed |  |  | 0
10 | Closed |  |  | 0
11 | Closed |  |  | 0
12 | Closed |  |  | 0
13 | Closed |  |  | 0
14 | Closed |  |  | 0
15 | Closed |  |  | 0
16 | Closed |  |  | 0
17 | Closed |  |  | 0
18 | Closed |  |  | 0
19 | Closed |  |  | 0
20 | Closed |  |  | 0
21 | Closed |  |  | 0
22 | Closed |  |  | 0
23 | Closed |  |  | 0
24 | Closed |  |  | 0
25 | Closed |  |  | 0
26 | Closed |  |  | 0
27 | Closed | Written |  | 0
28 | Closed |  |  | 0
29 | Closed |  |  | 0
30 | Closed |  |  | 0
31 | Closed |  |  | 0
32 | Closed |  |  | 0
33 | Closed |  |  | 0
34 | Closed |  |  | 0
35 | Closed |  |  | 0
36 | Closed |  |  | 0
37 | Closed |  |  | 0
38 | Closed |  |  | 0
39 | Closed |  |  | 0
40 | Closed |  |  | 0
41 | Closed |  |  | 0
42 | Closed |  |  | 0
43 | Closed |  |  | 0
44 | Closed |  |  | 0
45 | Closed |  |  | 0
46 | Closed |  |  | 0
47 | Closed |  |  | 0
48 | Closed |  |  | 0
49 | Closed |  |  | 0
50 | Closed |  |  | 0
51 | Closed |  |  | 0
52 | Closed |  |  | 0
53 | Closed |  |  | 0
54 | Closed |  |  | 0
55 | Closed |  |  | 0
56 | Closed |  |  | 0
57 | Closed |  |  | 0
58 | Closed |  |  | 0
59 | Closed |  |  | 0
60 | Closed |  |  | 0
61 | Closed |  |  | 0
62 | Closed |  |  | 0
63 | Closed |  |  | 0
64 | Closed |  |  | 0
65 | Closed |  |  | 0
66 | Closed |  |  | 0
67 | Closed |  |  | 0
68 | Closed |  |  | 0
69 | Closed |  |  | 0
70 | Closed |  |  | 0
71 | Closed |  |  | 0
72 | Closed |  |  | 0
73 | Closed |  |  | 0
74 | Closed |  |  | 0
75 | Closed |  |  | 0
76 | Closed |  |  | 0
77 | Closed |  |  | 0
78 | Closed |  |  | 0
79 | Closed |  |  | 0
80 | Closed |  |  | 0
81 | Closed |  |  | 0
82 | Closed |  |  | 0
83 | Closed |  |  | 0
84 | Closed |  |  | 0
85 | Closed |  |  | 0
86 | Closed |  |  | 0
87 | Closed |  |  | 0
88 | Closed |  |  | 0
89 | Closed |  |  | 0
90 | Closed |  |  | 0
91 | Closed |  |  | 0
92 | Closed |  |  | 0
93 | Singer | Written |  | 0
94 | Closed |  |  | 0
95 | Closed |  |  | 0
96 | Closed |  |  | 0
97 | Closed |  |  | 0
98 | Closed |  |  | 0
99 | Closed |  |  | 0
100 | Closed |  |  | 0
101 | Closed |  |  | 0
102 | Closed |  |  | 0
103 | Closed |  |  | 0
104 | Closed |  |  | 0
105 | Closed |  |  | 0
106 | Closed |  |  | 0
107 | Closed |  |  | 0
108 | Closed |  |  | 0
109 | Closed |  |  | 0
110 | Closed |  |  | 0
111 | Closed |  |  | 0
112 | Singer | Written |  | 0
113 | Closed |  |  | 0
114 | Closed |  |  | 0
115 | Closed |  |  | 0
116 | Closed |  |  | 0
117 | Closed |  |  | 0
118 | Closed |  |  | 0
119 | Closed |  |  | 0
120 | Closed |  |  | 0
121 | Closed |  |  | 0
122 | Closed |  |  | 0
123 | Closed |  |  | 0
124 | Closed |  |  | 0
125 | Closed |  |  | 0
126 | Closed |  |  | 0
127 | Closed |  |  | 0
128 | Closed |  |  | 0
129 | Closed |  |  | 0
130 | Closed |  |  | 0
131 | Closed |  |  | 0
132 | Closed |  |  | 0
133 | Closed |  |  | 0
134 | Closed |  |  | 0
135 | Closed |  |  | 0
136 | Closed |  |  | 0
137 | Closed |  |  | 0
138 | Closed |  |  | 0
139 | Closed |  |  | 0
140 | Closed |  |  | 0
141 | Closed |  |  | 0
142 | Closed |  |  | 0
143 | Closed |  |  | 0
144 | Closed |  |  | 0
145 | Closed |  |  | 0
146 | Closed |  |  | 0
147 | Closed |  |  | 0
148 | Closed |  |  | 0
149 | Closed |  |  | 0
150 | Closed |  |  | 0
151 | Closed |  |  | 0
152 | Closed |  |  | 0
153 | Closed |  |  | 0
154 | Closed |  |  | 0
155 | Closed |  |  | 0
156 | Closed |  |  | 0
157 | Closed |  |  | 0
158 | Closed |  |  | 0
159 | Closed |  |  | 0
160 | Closed |  |  | 0
161 | Closed |  |  | 0
162 | Closed |  |  | 0
163 | Closed |  |  | 0
164 | Closed |  |  | 0
165 | Closed |  |  | 0
166 | Closed |  |  | 0
167 | Closed |  |  | 0
168 | Closed |  |  | 0
169 | Closed |  |  | 0
170 | Closed |  |  | 0
171 | Closed |  |  | 0
172 | Closed |  |  | 0
173 | Closed |  |  | 0
174 | Closed |  |  | 0
175 | Closed |  |  | 0
176 | Closed |  |  | 0
177 | Closed |  |  | 0
178 | Closed |  |  | 0
179 | Closed |  |  | 0
180 | Closed |  |  | 0
181 | Closed |  |  | 0
182 | Closed |  |  | 0
183 | Closed |  |  | 0
184 | Closed |  |  | 0
185 | Closed |  |  | 0
186 | Closed |  |  | 0
187 | Closed |  |  | 0
188 | Closed |  |  | 0
189 | Closed |  |  | 0
190 | Closed |  |  | 0
191 | Closed |  |  | 0
192 | Closed |  |  | 0
193 | Closed |  |  | 0
194 | Closed |  |  | 0
195 | Closed |  |  | 0
196 | Closed |  |  | 0
197 | Closed |  |  | 0
198 | Closed |  |  | 0
199 | Closed |  |  | 0
200 | Closed |  |  | 0
201 | Closed |  |  | 0
202 | Closed |  |  | 0
203 | Closed |  |  | 0
204 | Closed |  |  | 0
205 | Closed |  |  | 0
206 | Closed |  |  | 0
207 | Closed |  |  | 0
208 | Closed |  |  | 0
209 | Closed |  |  | 0
210 | Closed |  |  | 0
211 | Closed |  |  | 0
212 | Closed |  |  | 0
213 | Closed |  |  | 0
214 | Closed |  |  | 0
215 | Closed |  |  | 0
216 | Closed |  |  | 0
217 | Closed |  |  | 0
218 | Closed |  |  | 0
219 | Closed |  |  | 0
220 | Closed |  |  | 0
221 | Closed |  |  | 0
222 | Closed |  |  | 0
223 | Closed |  |  | 0
224 | Closed |  |  | 0
225 | Closed |  |  | 0
226 | Closed |  |  | 0
227 | Closed |  |  | 0
228 | Closed |  |  | 0
229 | Closed |  |  | 0
230 | Closed |  |  | 0
231 | Closed |  |  | 0
232 | Closed |  |  | 0
233 | Closed |  |  | 0
234 | Closed |  |  | 0
235 | Closed |  |  | 0
236 | Closed |  |  | 0
237 | Closed |  |  | 0
238 | Closed |  |  | 0
239 | Closed |  |  | 0
240 | Closed |  |  | 0
241 | Closed |  |  | 0
242 | Closed |  |  | 0
243 | Closed |  |  | 0
244 | Closed |  |  | 0
245 | Closed |  |  | 0
246 | Closed |  |  | 0
247 | Closed |  |  | 0
248 | Closed |  |  | 0
249 | Closed |  |  | 0
250 | Closed |  |  | 0
251 | Closed |  |  | 0
252 | Closed |  |  | 0
253 | Closed |  |  | 0
254 | Closed |  |  | 0
255 | Closed |  |  | 0
256 | Closed |  |  | 0
257 | Closed |  |  | 0
258 | Closed |  |  | 0
259 | Closed |  |  | 0
260 | Closed |  |  | 0
261 | Closed |  |  | 0
262 | Closed |  |  | 0
263 | Closed |  |  | 0
264 | Closed |  |  | 0
265 | Closed |  |  | 0
266 | Closed |  |  | 0
267 | Closed |  |  | 0
268 | Closed |  |  | 0
269 | Closed |  |  | 0
270 | Closed |  |  | 0
271 | Closed |  |  | 0
272 | Closed |  |  | 0
273 | Closed |  |  | 0
274 | Closed |  |  | 0
275 | Closed |  |  | 0
276 | Closed |  |  | 0
277 | Closed |  |  | 0
278 | Closed |  |  | 0
279 | Closed |  |  | 0
280 | Closed |  |  | 0
281 | Closed |  |  | 0
282 | Closed |  |  | 0
283 | Closed |  |  | 0
284 | Closed |  |  | 0
285 | Closed |  |  | 0
286 | Closed |  |  | 0
287 | Closed |  |  | 0
288 | Closed |  |  | 0
289 | Closed |  |  | 0
290 | Closed |  |  | 0
291 | Closed |  |  | 0
292 | Closed |  |  | 0
293 | Closed |  |  | 0
294 | Closed |  |  | 0
295 | Closed |  |  | 0
296 | Closed |  |  | 0
297 | Closed |  |  | 0
298 | Closed |  |  | 0
299 | Closed |  |  | 0
300 | Closed |  |  | 0
301 | Closed |  |  | 0
302 | Closed |  |  | 0
303 | Closed |  |  | 0
304 | Closed |  |  | 0
305 | Closed |  |  | 0
306 | Closed |  |  | 0
307 | Closed |  |  | 0
308 | Closed |  |  | 0
309 | Closed |  |  | 0
310 | Closed |  |  | 0
311 | Closed |  |  | 0
312 | Closed |  |  | 0
313 | Closed |  |  | 0
314 | Closed |  |  | 0
315 | Closed |  |  | 0
316 | Closed |  |  | 0
317 | Closed |  |  | 0
318 | Closed |  |  | 0
319 | Closed |  |  | 0
320 | Closed |  |  | 0
321 | PM |  |  | 0
322 | Closed |  |  | 0
323 | Closed |  |  | 0
324 | PM |  |  | 0
325 | Closed |  |  | 0
326 | Closed |  |  | 0
327 | Closed |  |  | 0
328 | Closed |  |  | 0
329 | Closed |  |  | 0
330 | Closed |  |  | 0
331 | Closed |  |  | 0
332 | Closed |  |  | 0
333 | Closed |  |  | 0
334 | Closed |  |  | 0
335 | Closed |  |  | 0
336 | Closed |  |  | 0
337 | Closed |  |  | 0
338 | Closed |  |  | 0
339 | PM |  |  | 0
340 | Closed |  |  | 0
341 | Closed |  |  | 0
342 | Closed |  |  | 0
343 | PM |  |  | 0
344 | Closed |  |  | 0
345 | Closed |  |  | 0
346 | Closed |  |  | 0
347 | Closed |  |  | 0
348 | Closed |  |  | 0
349 | Closed |  |  | 0
350 | Closed |  |  | 0
351 | Closed |  |  | 0
352 | Closed |  |  | 0
353 | Closed |  |  | 0
354 | Closed |  |  | 0
355 | Closed |  |  | 0
356 | Closed |  |  | 0
357 | Closed |  |  | 0
358 | PM |  |  | 0
359 | Closed |  |  | 0
360 | PM |  |  | 0
361 | PM |  |  | 0
362 | Closed |  |  | 0
363 | PM |  |  | 0
364 | PM |  |  | 0
365 | Closed |  |  | 0
366 | Closed |  |  | 0
367 | Closed |  |  | 0
368 | Closed |  |  | 0
369 | Closed |  |  | 0
370 | Closed |  |  | 0
371 | Closed |  |  | 0
372 | Closed |  |  | 0
373 | Closed |  |  | 0
374 | Closed |  |  | 0
375 | Closed |  |  | 0
376 | Closed |  |  | 0
377 | Closed |  |  | 0
378 | Closed |  |  | 0
379 | Closed |  |  | 0
380 | Closed |  |  | 0
381 | Closed |  |  | 0
382 | Closed |  |  | 0
383 | Closed |  |  | 0
384 | Closed |  |  | 0
385 | Closed |  |  | 0
386 | Closed |  |  | 0
387 | Closed |  |  | 0
388 | Closed |  |  | 0
389 | Closed |  |  | 0
390 | Closed |  |  | 0
391 | Closed |  |  | 0
392 | Closed |  |  | 0
393 | Closed |  |  | 0
394 | Closed |  |  | 0
395 | Closed |  |  | 0
396 | Closed |  |  | 0
397 | Closed |  |  | 0
398 | Closed |  |  | 0
399 | Closed |  |  | 0
400 | Closed |  |  | 0
401 | Closed |  |  | 0
402 | Closed |  |  | 0
403 | Closed |  |  | 0
404 | Closed |  |  | 0
405 | Closed |  |  | 0
406 | Closed |  |  | 0
407 | Closed |  |  | 0
408 | Closed |  |  | 0
409 | Closed |  |  | 0
410 | Closed |  |  | 0
411 | Closed |  |  | 0
412 | Closed |  |  | 0
413 | Closed |  |  | 0
414 | Closed |  |  | 0
415 | Closed |  |  | 0
416 | Closed |  |  | 0
417 | Closed |  |  | 0
418 | Closed |  |  | 0
419 | Closed |  |  | 0
420 | Closed |  |  | 0
421 | Closed |  |  | 0
422 | Closed |  |  | 0
423 | Closed |  |  | 0
424 | Closed |  |  | 0
425 | Closed |  |  | 0
426 | Closed |  |  | 0
427 | Closed |  |  | 0
428 | Closed |  |  | 0
429 | Closed |  |  | 0
430 | Closed |  |  | 0
431 | Closed |  |  | 0
432 | Closed |  |  | 0
433 | Closed |  |  | 0
434 | Closed |  |  | 0
435 | Closed |  |  | 0
436 | Closed |  |  | 0
437 | Closed |  |  | 0
438 | Closed |  |  | 0
439 | Closed |  |  | 0
440 | Closed |  |  | 0
441 | Closed |  |  | 0
442 | Closed |  |  | 0
443 | Closed |  |  | 0
444 | Closed |  |  | 0
445 | Closed |  |  | 0
446 | Closed |  |  | 0
447 | Closed |  |  | 0
448 | Closed |  |  | 0
449 | Closed |  |  | 0
450 | Closed |  |  | 0
451 | Closed |  |  | 0
452 | Closed |  |  | 0
453 | Closed |  |  | 0
454 | Closed |  |  | 0
455 | Closed |  |  | 0
456 | Closed |  |  | 0
457 | Closed |  |  | 0
458 | Closed |  |  | 0
459 | Closed |  |  | 0
460 | Closed |  |  | 0
461 | Closed |  |  | 0
462 | Closed |  |  | 0
463 | Closed |  |  | 0
464 | Closed |  |  | 0
465 | Closed |  |  | 0
466 | Closed |  |  | 0
467 | Closed |  |  | 0
468 | Closed |  |  | 0
469 | Closed |  |  | 0
470 | Closed |  |  | 0
471 | Closed |  |  | 0
472 | Closed |  |  | 0
473 | Closed |  |  | 0
474 | Closed |  |  | 0
475 | Closed |  |  | 0
476 | Closed |  |  | 0
477 | Closed |  |  | 0
478 | Closed |  |  | 0
479 | Closed |  |  | 0
480 | Closed |  |  | 0
481 | Closed |  |  | 0
482 | Closed |  |  | 0
483 | Closed |  |  | 0
484 | Closed |  |  | 0
485 | Closed |  |  | 0
486 | Closed |  |  | 0
487 | Closed |  |  | 0
488 | Closed |  |  | 0
489 | Closed |  |  | 0
490 | Closed |  |  | 0
491 | Closed |  |  | 0
492 | Closed |  |  | 0
493 | Closed |  |  | 0
494 | Closed |  |  | 0
495 | Closed |  |  | 0
496 | Closed |  |  | 0
497 | Closed |  |  | 0
498 | Closed |  |  | 0
499 | Closed |  |  | 0
500 | Closed |  |  | 0
501 | Closed |  |  | 0
502 | Closed |  |  | 0
503 | Closed |  |  | 0
504 | Closed |  |  | 0
505 | Closed |  |  | 0
506 | Closed |  |  | 0
507 | Closed |  |  | 0
508 | Closed |  |  | 0
509 | Closed |  |  | 0
510 | Closed |  |  | 0
511 | Closed |  |  | 0
512 | Closed |  |  | 0
513 | Closed |  |  | 0
514 | Closed |  |  | 0
515 | Closed |  |  | 0
516 | Closed |  |  | 0
517 | Closed |  |  | 0
518 | Closed |  |  | 0
519 | Closed |  |  | 0
520 | Closed |  |  | 0
521 | Closed |  |  | 0
522 | Closed |  |  | 0
523 | Closed |  |  | 0
524 | Closed |  |  | 0
525 | Closed |  |  | 0
526 | Closed |  |  | 0
527 | Closed |  |  | 0
528 | Closed |  |  | 0
529 | Closed |  |  | 0
530 | Closed |  |  | 0
531 | Closed |  |  | 0
532 | Closed |  |  | 0
533 | Closed |  |  | 0
534 | Closed |  |  | 0
535 | Closed |  |  | 0
536 | Closed |  |  | 0
537 | Closed |  |  | 0
538 | Closed |  |  | 0
539 | Closed |  |  | 0
540 | Closed |  |  | 0
541 | Closed |  |  | 0
542 | Closed |  |  | 0
543 | Closed |  |  | 0
544 | Closed |  |  | 0
545 | Closed |  |  | 0
546 | Closed |  |  | 0
547 | Closed |  |  | 0
548 | Closed |  |  | 0
549 | Closed |  |  | 0
550 | Closed |  |  | 0
551 | Closed |  |  | 0