{"text_format":"1","workbook":"xlsx","n_sheets":9,"sheets":["Mar 2019 tasks","Jan 2019 tasks","Nov 2018 tasks","D1.0 review points","D1.0 text neede","Sept 2018 tasks","July 2018 tasks","Action Items","D 1.0 tasks"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Mar 2019 tasks","index":0,"n_rows":10,"n_cols":6,"rows_kept":10,"cut":false,"hidden":false,"merged":[[0,0,0,1],[0,4,0,5]]}
["Due by 04/2019 mtg",null,null,null,"Presented at AdHoc"]
["Clause","Description","Volunteer","D1.2 Comments submitted","2019-03-20","2019-04-03"]
["104.1.3","Need differentiation of Types B & F","PoDL - Heath"]
["44.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta:  Need to fill in TBD values","William Lo",null,null,"X"]
["125.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta, Maximum (ns):  Need to fill in TBD values","William Lo",null,null,"X"]
["149.3.8.2.5","The OAM request to exit LPI is unneeded. Commenters are requested to provide text and edits necessary to cleanly remove this function and describe the local fault mechanism for the RS to signal exit from LPI.  This is due to the use of XGMII instead of GMII used by 1000BASE-T1.","Brett McClellan"]
["149.4.2.4.6","SEND_S is both the name of a mode and a sequence. Commenters are encouraged to propose text changes to correct this issue.","George Zimmerman"]
["149.5.3.2","Alien crosstalk noise rejection - needs The noise level needs to be determined jointly with adding an alien crosstalk coupling specification to the link segment.\nAlso need coupling between link segments for the cabling (measure 6 around 1 for 15m).","\nThomas Mueller\n\nhttp://www.ieee802.org/3/ch/email/msg00391.html"]
["149.7.2.2","PSAACR-F Need equations and final text.","\nThomas Mueller"]
[null,"PICS - To be added to D1.3 based on D1.2 content.","Kae Dube / \nCurtis Donahue"]

{"sheet":"Jan 2019 tasks","index":1,"n_rows":26,"n_cols":7,"rows_kept":26,"cut":false,"hidden":false,"merged":[[0,0,0,1],[0,4,0,6]]}
["Due by 03/2019 mtg",null,null,null,"Presented at AdHoc"]
["Clause","Description","Volunteer","D1.1 Comments submitted","2019-01-30","2019-02-13","2019-02-27"]
["45.2.1.192.1\n45.2.3.79","Concern that this statement conflicts with \"fast start-up\": The control and\nmanagement interface shall be restored to operation within 0.5 s from the setting of bit 1.2309.15.\nPropose that requirement be proposed for clause 149 which can be referenced from here.","Natalie Wienckowski\nGerrit den Beseten","284, 295"]
["45.2.1.192.3","Concern that this statement conflicts with \"fast start-up\": may take many seconds to run at optimum error ratio after exiting from reset or lowpower mode.\nPropose that requirement be proposed for clause 149 which can be referenced from here.","Gerrit den Beseten","293, 296"]
["104.1.3","Need differentiation of Types B & F","PoDL - Heath"]
["149.5.1","Comment #157 - TX_CLK_DIV is 1/16 TX_CLK.  Is this the correct value?","William Lo",62]
["149.4.2.4.10","This clause should be informative only.  May need to be rewritten and requirements may need to be moved to the appropriate clauses.","George Z & others","231:  complete rewrite of section\nRewrite of some:  59, 87, 88, 60, 89, 90, 91\nEditorial only: 100, 178"]
["44.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta:  Need to fill in TBD values"]
["125.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta, Maximum (ns):  Need to fill in TBD values"]
["149.3.7.2\n149.4.2.3","RFER - Reed-Solomon Block error rate",null,"Conflicting numbers in 105, 225, 289."]
["149.5.2.5","Need maximum peak output voltage.  This was not provided with the PSD text.",null,"Proposal to remove:  227\nDifferent values: 275, 291"]
["149.7.1.5","Need additional text for Shielding attenuation and details on test method.","Thomas Mueller","Presentation for March, draft has been provided."]
["149.3.2.2.20\n149.3.2.2.21\n149.3.6.2.2\n149.3.6.2.3\n149.3.8.4.3","Still need Alert/Low Power (EEE) requirements.\n\n\n\nrx_boundary / tx_boundary","Jim Graba / Saied Benyamin ","48, 98\n82, 64, 28, 29, 30\n79, \n80, 219, 81\n123, 39, 40"]
["149.3.2.2.22","Need EEE state diagram","Jim Graba / Saied Benyamin","http://www.ieee802.org/3/ch/public/mar19/Graba_3ch_1_0319.pdf"]
["149.3.2.3","Training sequence.","Mike Tu","86, 277, 31"]
["149.3.6.3","State diagrams summary","Mike Tu","Needs checking:  101 & 221\n222,103, 78"]
["149.3.7.3","Loopback signal","Mike Tu","93, 224 similar\n306 is different"]
["149.4.2.7","Refresh","Jim Graba / Saied Benyamin","61 & 75 conflict\n77 - which figure?"]
["149.5.1","Test modes",null,"243\nStill need P152 L44."]
["149.5.2.1","Output droop"]
["149.5.2.2","Tranmitter distorition - Test mode 4",null,"Curtis D will try to prepare a presentation"]
["149.5.2.3","Transmitter timing jitter - Test mode 2"]
["149.5.3.2","Alien crosstalk noise rejection - needs to be completed or deleted.\nAlso need coupling between link segments for the cabling (measure 6 around 1 for 15m).","George Z - info on how to test.\nThomas Mueller - create test devices and test them.","Thomas still working"]
["149.6.1","Auto-Neg - either content or comment to remove Editor's Note.","George Z",230]
["149.2.2.9.3","Need suggetion for additional control codes or comment to remove Editor's Note."]
["149.3.6.2.5","Counters","Mike Tu / George Z","102, 220"]

{"sheet":"Nov 2018 tasks","index":2,"n_rows":20,"n_cols":6,"rows_kept":20,"cut":false,"hidden":false,"merged":[[0,0,0,1],[0,3,0,5]]}
["Due by 01/2019 mtg",null,null,"Presented at AdHoc"]
["Section","Description","Volunteer","2018-12-05","2018-12-19","2019-01-02"]
["44.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta","Use text from 126 with TBDs"]
["125.3\n149.10","Delay constraints - Maximum bit time, Maximum pause quanta, Maximum (ns)","Use text from 126 with TBDs"]
["149.1.3.1","Data mode scrambler seed","Mike Tu"]
["149.3.x","Figure 136-x Need to know if an exisiting Figure should be referenced or need the correct figure.","Paul Langner"]
["149.3.2.3","Need text for Normal PCS Receive function operation.","George Z.\nBased on first 5 paragraphs of 126.3.2.3?  Needs updated as we only have one pair."]
["149.3.2.3.2","PCS descrambler","Mike Tu - Text okay as is."]
["149.3.2.3.3","List of Invalid blocks conditions","Brett McClellan"]
["149.3.2.2.19","Need to decide what to replace highlighted note with."]
["149.3.3","Test-pattern generators - Need transmit and receive diagrams.","Figure numbers were added to D1.0."]
["149.3.4.6","PMA training mode descrambler polynomials - all yellow","Same as 149.3.2.3.2 - Mike Tu - Text okay as is."]
["149.1.3.3, 149.3.2.2.1, 149.3.2.2.21, 149.3.5.3, 149.4.2.7","Refresh period signaling - was not finalized in Bangkok. <Alert/Wake>"]
["149.3.6","Need complete State Diagrams section","Mike Tu provided as comment #69"]
["149.4.2.3","RFER - Reed-Solomon Block error rate"]
["149.4.2.4","Can be comment for draft to use tu_3ch_04_1018.pdf slides 4 to 7 with or without changes.","Mike Tu will provide updated presentations"]
["149.5.1","Test clock frquency & need final details on all test modes, much of this is still yellow","George Zimmerman, except clock frequency"]
["149.5.2","Output droop - need timing"]
["149.5.2.5","Need maximum peak output voltage.  This was not provided with the PSD text."]
["149.7.1.5","Need additional text for Shielding attenuation and details on test method."]

{"sheet":"D1.0 review points","index":3,"n_rows":5,"n_cols":2,"rows_kept":5,"cut":false,"hidden":false,"merged":[]}
["Section"]
["45.2.3 OAM Registers","The text describing the OAM registers was added under editorial license and needs to be carefully reviewed and aligned with the text in clause 149. The editor and content provider noticed that there were technical choices to be made in aligning the text. Commenters are encouraged to review and comment on the register arrangement of the extra 4 bytes."]
["149.4.5, Figure 149-21","Link Monitor - This was slide 10 of souvigner_3ch_03a_1118.pdf.   There was not a motion to adopt this, but thse changes were required to match the states in the PHY Control state diagram which were adopted."]
["149.3.8","New name for OAM?"]
["149.3.8.2.1","\"dummy\" OAM sent when transitioning from LPI to normal operation.  Please see presentation http://www.ieee802.org/3/ch/public/adhoc/Lo_3ch_02_1218.pdf for details."]

{"sheet":"D1.0 text neede","index":4,"n_rows":20,"n_cols":5,"rows_kept":20,"cut":false,"hidden":false,"merged":[]}
["Motion #","Description","Mover","Seconder","Provider"]
[4,"Scrambler for all modes","Tom Souvignier","Brett McClellan","NA"]
[5,"LPI - need text or example Clause & State diagrams","Tom Souvignier","Saied Benyamin","Mike Tu, Jim Grabba, Tom Souvignier"]
[6,"PSD masks - need info on what is transmitted for Test mode 5 for the measurement","Tom Souvignier","Gerrit den Besten","Assume idles are transmitted.\nGeorge will try to provide a reference."]
[7,"PoDL","Olaf Grau","Christoph Wechsler","NA"]
[8,"PoDL","Olaf Grau","Christoph Wechsler","NA"]
[9,"OAM - need text including RS(16,14)","William Lo","Saied Benyamin","William Lo"]
[10,"OAM Sttus bytes","Christoph Wechsler","Sujan Pandey","Natalie Wienckowski"]
[11,"FEC Interleaving","Sujan Pandey","William Lo","William Lo"]
[12,"PCS diagrams","Tom Souvignier","William Lo","NA"]
[13,"Link Segment Frequency ranges","Gerrit den Besten","Josef Ohni","NA"]
[14,"Link delay frequency ranges","Gerrit den Besten","Ricky Vernickel","NA"]
[15,"MDI Return loss frequency ranges","Gerrit den Besten","Thomas Müller","NA"]
[16,"Sheilding Attenution - provide text or clause with example text","Gerrit den Besten","Thomas Müller","George Zimmerman"]
[17,"IL limit line","Gerrit den Besten","Ricky Vernickel","NA"]
[18,"2.5G RL","Gerrit den Besten","Josef Ohni","NA"]
[19,"5G RL","Gerrit den Besten","Thomas Müller","NA"]
[20,"10G RL","Gerrit den Besten","Ricky Vernickel","NA"]
[21,"Clause 45 - Need new OAM registers","Brett McClellan","Olaf Grau","George Zimmerman"]
[22,"Test Mode 3 - Don't need graphs in text","Conrad Zerna","Olaf Grau","George Zimmerman"]

{"sheet":"Sept 2018 tasks","index":5,"n_rows":21,"n_cols":7,"rows_kept":21,"cut":false,"hidden":false,"merged":[[0,3,0,6],[0,0,0,1]]}
["Due by 11/2018 mtg",null,null,"Presented at AdHoc"]
["Section","Description","Volunteer","2018-09-19","2018-10-03","2018-10-17","2018-10-31"]
[null,"Interleaver Depth at each speed","Tu",null,null,"planned"]
[null,"IL limit for 2.5GBASE-T1","Gerrit",null,null,null,"planned"]
[null,"Shielding Attenuation for each speed","Gerrit",null,null,null,"planned"]
["149.5.3.5","Transmit Differential signal voltage, PSD"]
[149.69999999999999,"Align maximum frequency of all link segment parameters to be the same.  Current IL is 3000 MHz and RL is 5500 MHz.","Gerrit",null,null,null,"planned"]
["149.10","Delay Constraints also in 44.3 and 125.3"]
["45","Registers for all speeds","George Zimmerman",null,null,"planned"]
["78.2, 149.3.5","EEE Parameters, LPI signaling","Langner, Saied, Graba",null,"planned","planned"]
["104","PoDL text","Heath, Gitesh"]
["149.3.2.2.12","PCS Scrambler","Tu, Sujan",null,"planned",null,"planned"]
["149.4.3.2","RFER (Receive Frame Error Rate)"]
["149.4.2.4","PHY Control function","Tu"]
["149.4.4","PMA State variables"]
["149.4.5","Startup sequence","Tu",null,"planned"]
["149.5.2","Test Modes - don't forget additional modes for selectable fixed precoder","Langner"]
["149.5.4.2","Alien crosstalk noise rejection test parameters."]
["149.6.1","Additional Auto-Negotiation functions"]
["149.3.8","OAM Frame definition","Langner, Lo, Wienckowski",null,"planned","planned"]
[null,"Training - Where superframe starts with interleaving"]

{"sheet":"July 2018 tasks","index":6,"n_rows":15,"n_cols":3,"rows_kept":15,"cut":false,"hidden":false,"merged":[]}
["Motion","Desc","Owner ( due 8am EDT 7/23/18)"]
[4,"PAM 4 @ all speeds","George Z"]
[5,"IL eq change","Natalie"]
[6,"Impedance","Natalie"]
[7,"Link Synchronization","Mike Tu"]
[8,"Baud rate","George Z"]
[9,"OAM","Natalie"]
[10,"10-bit RS symbol","for next step"]
[]
["SP"]
[7,"Burst length - more info","Olaf K will provide info on what pulses are in a vehicle - 8/8/18\nerror propagation statistics - everyone to determine themselves based on their assumptions and Olaf's data"]
[11,"IL change to 26 gauge @ 11 m","Gerrit 8/8/18"]
[12,"Looser IL for 2.5 Gbps","Eric - 8/22/18"]
["13, 14","Optional Asymmetric data","Tom S & Gerrit - 8/22/18"]
[null,"OAM usage definition","Jim & Natalie"]

{"sheet":"Action Items","index":7,"n_rows":33,"n_cols":48,"rows_kept":33,"cut":false,"hidden":false,"merged":[[1,2,1,22],[1,23,1,47],[2,2,2,3],[2,4,2,5],[2,6,2,8],[2,9,2,10],[2,11,2,12],[2,13,2,14],[2,15,2,16],[2,17,2,19],[2,45,2,46],[2,20,2,21],[2,23,2,24],[2,25,2,26],[2,27,2,28],[2,29,2,30],[2,42,2,44],[2,31,2,33],[2,36,2,37],[2,34,2,35],[2,38,2,39],[2,40,2,41]]}
[null,"On Track"]
[null,"Started, risk of being late",2018,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2019]
[null,"late","Mar",null,"Apr",null,"May",null,null,"Jun",null,"Jul",null,"Aug",null,"Sep",null,"Oct",null,null,"Nov",null,"Dec","Jan",null,"Feb",null,"Mar",null,"Apr",null,"May",null,null,"Jun",null,"Jul",null,"Aug",null,"Sep",null,"Oct",null,null,"Nov",null,"Dec"]
[null,"due date","7,8",21,4,18,2,16,"24,25",13,27,"PL",25,8,22,5,"IN",3,17,31,"PL",28,12,9,"IN",6,20,6,"PL",3,17,1,15,"IN",12,26,10,"PL",7,21,4,"IN",2,16,30,"PL",27,11]
[null,"OEM Topology"]
[null,"Consolidated Topology"]
[null,"OEM Power Consumption Expectations"]
[null,"PoDL and Power Budget"]
[null,"Cabling System Model - IL & RL"]
[null,"Thomas Mueller"]
[null,"Eric DiBiaso"]
[null,"Signaling type and modulation (2.5 Gb/s & 10 Gb/s)"]
[null,"Sujan Pandey"]
[null,"Tom Souvignier"]
[null,"Peter Wu"]
[null,"Ramin Farjad"]
[null,"Tazhi Madgar"]
[null,"Conrad Zerna"]
[null,"EMC testing"]
[null,"PHY Vendor Needs"]
[null,"Test Data"]
[null,"Line Coding and FEC "]
[]
[]
[]
[]
[]
[]
[]
[]
[null,"Register Maps"]
[null,"EEE support"]
[null,"PICs"]

{"sheet":"D 1.0 tasks","index":8,"n_rows":27,"n_cols":3,"rows_kept":27,"cut":false,"hidden":false,"merged":[[0,0,0,2]]}
["What's still missing.  Major items only.  Minor stuff and corrections not covered here."]
["Based on ","0.4.1"]
["Date updated",{"$f":" LastSaveDate()","v":"2019-03-21T14:13:46"}]
[]
["Clause","Who to contribute text","Comments"]
[44,null,"Introduction to 10 Gb/s baseband network\nNeed to complete additions to add 10GBASE-T1."]
[45,"George","Management Data Input/Output (MDIO) Interface\nCollected from information in Clauses 149 & 150.\nShould OAM be added?"]
[78,null,"Energy-Efficient Ethernet (EEE)\nSomeone needs to provide the timing information for the rows to be added."]
[104,null,"PoDL"]
[125,null,"Introduction to 2.5 Gb/s and 5 Gb/s networks\nNeed to modify to add references to 2.5GBASE-T1 and 5GBASE-T1"]
["149, 149.1.1, 149.1.2","Natalie","Fill in open spots based on remainder of content in Clause 149."]
["149.1.3.1",null,"Overview - Physical Coding Sublayer (PCS)"]
["149.1.3.3",null,"EEE capability"]
["149.1.3.4",null,"Link Synchronization"]
["149.1.4",null,"Signaling"]
[149.19999999999999,null,"2.5GBASE-T1 service primitives and interfaces"]
[149.30000000000001,null,"2.5GBASE-T1 Physical Coding Sublayer (PCS) functions\nAdd OAM"]
[149.4,null,"Physical Medium Attachment (PMA) Sublayer"]
[149.5,null,"PMA electrical specifications - Test modes"]
[149.6,null,"Management interface"]
[149.69999999999999,null,"Link Segment"]
["149.7.x",null," Differential to common mode conversion/ common mode to differential mode conversion"]
["149.7.x",null,"Coupling parameters between link segments - alien xtalk"]
["149.7.x",null,"Coupling attenuation"]
["149.7.x",null,"Transfer Impedance "]
["149.10",null,"Delay constraints"]
[149.11000000000001,"Curtis","PICS"]