{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Sept 2018 tasks","July 2018 tasks","Action Items","D 1.0 tasks"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sept 2018 tasks","index":0,"n_rows":21,"n_cols":7,"rows_kept":21,"cut":false,"hidden":false,"merged":[[0,3,0,6],[0,0,0,1]]}
["Due by 11/2018 mtg",null,null,"Presented at AdHoc"]
["Section","Description","Volunteer","2018-09-19","2018-10-03","2018-10-17","2018-10-31"]
[null,"Interleaver Depth at each speed","Tu",null,null,"planned"]
[null,"IL limit for 2.5GBASE-T1","Gerrit",null,null,null,"planned"]
[null,"Shielding Attenuation for each speed","Gerrit",null,null,null,"planned"]
["149.5.3.5","Transmit Differential signal voltage, PSD"]
[149.69999999999999,"Align maximum frequency of all link segment parameters to be the same.  Current IL is 3000 MHz and RL is 5500 MHz.","Gerrit",null,null,null,"planned"]
["149.10","Delay Constraints also in 44.3 and 125.3"]
["45","Registers for all speeds","George Zimmerman",null,null,"planned"]
["78.2, 149.3.5","EEE Parameters, LPI signaling","Langner, Saied, Graba",null,"planned","planned"]
["104","PoDL text","Heath, Gitesh"]
["149.3.2.2.12","PCS Scrambler","Tu, Sujan",null,"planned",null,"planned"]
["149.4.3.2","RFER (Receive Frame Error Rate)"]
["149.4.2.4","PHY Control function","Tu"]
["149.4.4","PMA State variables"]
["149.4.5","Startup sequence","Tu",null,"planned"]
["149.5.2","Test Modes - don't forget additional modes for selectable fixed precoder","Langner"]
["149.5.4.2","Alien crosstalk noise rejection test parameters."]
["149.6.1","Additional Auto-Negotiation functions"]
["149.3.8","OAM Frame definition","Langner, Lo, Wienckowski",null,"planned","planned"]
[null,"Training - Where superframe starts with interleaving"]

{"sheet":"July 2018 tasks","index":1,"n_rows":15,"n_cols":3,"rows_kept":15,"cut":false,"hidden":false,"merged":[]}
["Motion","Desc","Owner ( due 8am EDT 7/23/18)"]
[4,"PAM 4 @ all speeds","George Z"]
[5,"IL eq change","Natalie"]
[6,"Impedance","Natalie"]
[7,"Link Synchronization","Mike Tu"]
[8,"Baud rate","George Z"]
[9,"OAM","Natalie"]
[10,"10-bit RS symbol","for next step"]
[]
["SP"]
[7,"Burst length - more info","Olaf K will provide info on what pulses are in a vehicle - 8/8/18\nerror propagation statistics - everyone to determine themselves based on their assumptions and Olaf's data"]
[11,"IL change to 26 gauge @ 11 m","Gerrit 8/8/18"]
[12,"Looser IL for 2.5 Gbps","Eric - 8/22/18"]
["13, 14","Optional Asymmetric data","Tom S & Gerrit - 8/22/18"]
[null,"OAM usage definition","Jim & Natalie"]

{"sheet":"Action Items","index":2,"n_rows":33,"n_cols":48,"rows_kept":33,"cut":false,"hidden":false,"merged":[[2,42,2,44],[2,31,2,33],[2,36,2,37],[2,34,2,35],[2,38,2,39],[2,40,2,41],[1,2,1,22],[1,23,1,47],[2,2,2,3],[2,4,2,5],[2,6,2,8],[2,9,2,10],[2,11,2,12],[2,13,2,14],[2,15,2,16],[2,17,2,19],[2,45,2,46],[2,20,2,21],[2,23,2,24],[2,25,2,26],[2,27,2,28],[2,29,2,30]]}
[null,"On Track"]
[null,"Started, risk of being late",2018,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2019]
[null,"late","Mar",null,"Apr",null,"May",null,null,"Jun",null,"Jul",null,"Aug",null,"Sep",null,"Oct",null,null,"Nov",null,"Dec","Jan",null,"Feb",null,"Mar",null,"Apr",null,"May",null,null,"Jun",null,"Jul",null,"Aug",null,"Sep",null,"Oct",null,null,"Nov",null,"Dec"]
[null,"due date","7,8",21,4,18,2,16,"24,25",13,27,"PL",25,8,22,5,"IN",3,17,31,"PL",28,12,9,"IN",6,20,6,"PL",3,17,1,15,"IN",12,26,10,"PL",7,21,4,"IN",2,16,30,"PL",27,11]
[null,"OEM Topology"]
[null,"Consolidated Topology"]
[null,"OEM Power Consumption Expectations"]
[null,"PoDL and Power Budget"]
[null,"Cabling System Model - IL & RL"]
[null,"Thomas Mueller"]
[null,"Eric DiBiaso"]
[null,"Signaling type and modulation (2.5 Gb/s & 10 Gb/s)"]
[null,"Sujan Pandey"]
[null,"Tom Souvignier"]
[null,"Peter Wu"]
[null,"Ramin Farjad"]
[null,"Tazhi Madgar"]
[null,"Conrad Zerna"]
[null,"EMC testing"]
[null,"PHY Vendor Needs"]
[null,"Test Data"]
[null,"Line Coding and FEC "]
[]
[]
[]
[]
[]
[]
[]
[]
[null,"Register Maps"]
[null,"EEE support"]
[null,"PICs"]

{"sheet":"D 1.0 tasks","index":3,"n_rows":36,"n_cols":3,"rows_kept":36,"cut":false,"hidden":false,"merged":[[0,0,0,2]]}
["What's still missing.  Major items only.  Minor stuff and corrections not covered here."]
["Based on ","0.4.1"]
["Date updated",{"$f":" LastSaveDate()","v":"2018-10-17T12:07:19"}]
[]
["Clause","Who to contribute text","Comments"]
[30,"Natalie","Management\nMost of this can be completed as information is provided in Clauses 149 & 150."]
[44,null,"Introduction to 10 Gb/s baseband network\nNeed to complete additions to add 10GBASE-T1."]
[45,"Natalie","Management Data Input/Output (MDIO) Interface\nCollected from information in Clauses 149 & 150.\nShould OAM be added?"]
[78,null,"Energy-Efficient Ethernet (EEE)\nSomeone needs to provide the timing information for the rows to be added."]
["98B.3",null,"Need to add bit definitions for 2.5GBASE-T1, 5GBASE-T1 and 10GBASE-T1. "]
["98.B.4","Natalie","Add 2.5GBASE-T1, 5GBASE-T1 and 10GBASE-T1 to Priority Resolution list from fastest to slowest."]
[104,null,"PoDL"]
[125,null,"Introduction to 2.5 Gb/s and 5 Gb/s networks\nNeed to modify to add references to 2.5GBASE-T1 and 5GBASE-T1"]
["149, 149.1, 149.2","Natalie","Fill in open spots based on remainder of content in Clause 149."]
["149.1.2.1",null,"Overview - Physical Coding Sublayer (PCS)"]
["149.1.2.2",null,"Overview - Physical Medium Attachment (PMA) sublayer"]
["149.1.2.3",null,"EEE capability"]
["149.1.2.4",null,"Link Synchronization"]
["149.1.3",null,"Signaling"]
["149.1.4","Natalie","Interfaces "]
["149.1.5","Natalie","Conventions - similar in all PHY Clauses"]
[149.19999999999999,null,"2.5GBASE-T1 service primitives and interfaces"]
[149.30000000000001,null,"2.5GBASE-T1 Physical Coding Sublayer (PCS) functions\nAdd OAM"]
[149.4,null,"Physical Medium Attachment (PMA) Sublayer"]
[149.5,null,"PMA electrical specifications"]
[149.6,null,"Management interface"]
[149.69999999999999,null,"Link Segment"]
["149.7.1.2","Natalie","Differential characteritic impedance\nNominal impedance of 100 ohms for cabling.  NO TOLERANCE!"]
["149.7.x",null," Differential to common mode conversion/ common mode to differential mode conversion"]
["149.7.x",null,"Maximum link delay"]
["149.7.x",null,"Coupling parameters between link segments - alien xtalk"]
["149.7.x",null,"Coupling attenuation"]
["149.7.x",null,"Transfer Impedance "]
[149.80000000000001,null,"MDI specification"]
["149.10",null,"Delay constraints"]
[149.11000000000001,"Curtis","PICS"]