## Ver17
[5 empty] | EVALUATION CRITERIA DOCUMENT (Ver. 17) STATUS |  |  | By Kitahara Minako and Radhakrishna Canchi | 2005-09-07
Section |  |  |  |  | Heading | Status | Comment |  | Detail status w.r.t. Version 17 As on tel conference on Sep.07, 2005
[7 empty] | Editors Notes | Details
1 |  |  |  |  | Overview | -
| 1.1 |  |  |  | Scope | Close
| 1.2 |  |  |  | Purpose | Close
| 1.3 |  |  |  | Organization of the Document | Close
2 |  |  |  |  | Link level and System Level Anlysis | Close
3 |  |  |  |  | Link level Modeling | -
| 3.1 |  |  |  | Modeling assumptions | Close
| 3.2 |  |  |  | Performance metrics | Close
4 |  |  |  |  | Traffic Models for 802.20 System Simulations | -
| 4.1 |  |  |  | Introduction | Close
| 4.2 |  |  |  | Context and Scope | -
|  | 4.2.1 |  |  | User Device Scenarios – For Information Only | Close
|  | 4.2.2 |  |  | Basis for Traffic Models | Close
|  | 4.2.3 |  |  | Adaptive applications | Close
| 4.3 |  |  |  | Traffic Models | Open | Option1/2（DanGal) | OP2：simple traffic mix | FOR OPTION#3: Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
|  | 4.3.1 |  |  | User/Traffic Modeling Approach | Close
|  | 4.3.2 |  |  | Packet Generation | Close
|  | 4.3.3 |  |  | Web Browsing | Close
|  | 4.3.4 |  |  | FTP | Close
|  | 4.3.5 |  |  | Voice (VoIP) | Open | Editor’s Notes: Proponents with other Options need to supply text for this section. Contribution C802.20-05/29 proposes voice quality testing. One voice codec, AMR, for simulations was proposed referencing IETF RFC 3267. Overall resolution for this section is required. | Needs to be updated w.r.t. C802.20-05/36 based on Groups consensus on E-Model based approach. | Dan Gal has provided some of his views based on C802.20-05/36. Canchi/Murakami san would update and provide the text/contributions
|  | 4.3.6 |  |  | Video (Videotelephony/Videoconferencing) | Open | Editor’s Note: Need a Contribution proposing Text OR Delete the section | Contribution or delete | Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
|  | 4.3.7 |  |  | Audio streaming | Open | Editor’s Note: Need a Contribution proposing Text OR Delete the section | Contribution or delete | Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
|  | 4.3.8 |  |  | Video streaming | Open | [Note: Need to confirm if the de-jitter buffer window size of 5 seconds needs to be changed for the higher data rate] | jitter buffa size : 5sec（OP1)/max 5sec（OP2) | Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
|  | 4.3.9 |  |  | Wireless Multi-Party Gaming Traffic | Open | Option1/2/3/4 | OP1:3GPP2 OP2:3GPP OP3:convine 2. OP4: from new literature | Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
|  |  | 4.3.9.1 |  | Reverse Link | Open | OP1
|  |  | 4.3.9.2 |  | Forward Link Model | Open | OP1
|  | 4.3.10 |  |  | Full buffers (Infinite backlog) model | Close
| 4.4 |  |  |  | Traffic Mix | Open | Editor’s Note: The Definition of Traffic Mix needs clarification. Option1[TBD]/2 （DanGal) | OP2：simple traffic mix | FOR OPTION 3 Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
5 |  |  |  |  | System Level Modeling | Close
| 5.1 |  |  |  | Simulation Flow and User Loading or Cell layout | Open | Option1/2 | Option1 (NEW:simulation flow and user loading) | some opinion existed that these are not options. Need to be updated!
|  | 5.1.1 |  |  | Distribution of users | Open | Option2
|  | 5.1.2 |  |  | User usage model | Open | [Note from CC on April 19: (i) Distributions need to be the same for the evaluation of various proposals; (ii) As a reference, similar distributions have been proposed in section 9.2: Channel mix] Editor’s Note: Clarification of this section needed or Delete. | Option2 Delete or clarify
| 5.2 |  |  |  | Higher Layer Protocol Modeling | Open |  | Dan Gal proposed new text | Please see Dan Gals' ContributionEval_Criteria_v17_section5.2rewriteproposal.doc
|  | 5.2.1 |  |  | TCP model | Close
|  |  | 5.2.1.1 |  | TCP Connection Set-up and Release Procedure | Close
|  |  | 5.2.1.2 |  | TCP slow start Model | Close
|  |  |  | 5.2.1.2.1 | UL (Uplink) slow start model | Close
|  |  |  | 5.2.1.2.2 | DL (Downlink) slow start model | Close
| 5.3 |  |  |  | Backhaul Network Modeling | -
|  | 5.3.1 |  |  | Network Delay model | Close
|  | 5.3.2 |  |  | Network Loss model | Close
| 5.4 |  |  |  | Mobility Modeling | Open | Editor’s Note: Adopted from Contribution 05/10r2 in Session #15 and the contributor requested to provide more details definitions of the metrics. | NEW TEXT | provided by Rajat Prakash
| 5.5 |  |  |  | Control signaling modeling | Open | Editor’s Note: This section now has two Options. | Option1: Delete the section Option2:Option 2: Text from C802.20-05/40 shown below. | follow up contributer(option2)
|  | 5.5.1 |  |  | DL signaling models | Open | MACstate transmission msg/Scheduling
|  | 5.5.2 |  |  | UL signaling models | Open | Access channel model/ ACK channel quality Feedback
6 |  |  |  |  | Phased Approach for Technology Evaluation | Close
| 6.1 |  |  |  | Phase 1 | Close
|  | 6.1.2 /6.1.1? |  |  | Phase1 calibration | Open | Editor’s Note: Also see Contributions C802.20-04/86r6 and C802.20-05/30 |  | contribution need( to move forward)
| 6.2 |  |  |  | Phase 2 | Open | phase2 conditions are TBD | Calibration/Apprication(WAP/Video Conf/E-mail/Multimedia Msｇ/Instant Msg/Audio Strieaming/PDA remote sync/File sharing/BCMCS(RDP/UDP)/Telematics）/Channel model/TCP modeling/Network model/ Mobility model/Control signaling model
7 |  |  |  |  | Link-System Interface (LSI) | Close
8 |  |  |  |  | System Simulation Calibration | Open | Editor’s Note: To be updated with the agreed upon version of the proposed text in contribution C802.20-04/83rX. Also see contribution C802.20-05/30 and 05/44.See C802.20-C05/30 05/44 |  | contribution needed ( to move forward)
| 8.1 |  |  |  | Step 1: Deterministic Calibration | Open | See C802.20-C05/30 05/44 |  | contribution needed ( to move forward)
| 8.2 |  |  |  | Step 2: Monte Carlo Simulation | Open | See C802.20-C05/30 05/44 |  | contribution needed ( to move forward)
| 8.3 |  |  |  | Outputs for calibration | Open | See C802.20-C05/30 05/44 |  | contribution needed ( to move forward)
| 8.4 |  |  |  | Further calibration | Close
9 |  |  |  |  | Channel Modeling | Close
| 9.1 |  |  |  | Channel Mix | Open | OPTION # 1: Delete the section {Editor’s Note: Straw Poll at May Interim was 10 Yes to delete and 1 No} OPTION # 2: ….[. Editor: I believe above is a reference to the Channel Models document. Editors Note: We eliminated 11 paths on the Channel Models document - - eliminate here? | OP1:delete OP2：channel mix1 OP3:channel mix2(detail version)
10 |  |  |  |  | RF Environment | - | Updated based on C802.20-04/64R4
| 10.1 |  |  |  | Radio Transceiver Characteristics | Close
|  | 10.1.1 |  |  | Transmitter | Open | Note that when applying the FCC emission attenuation formula (see Table 12, item 3, where P is the transmit powe{editor note: verify correctness} FCC emission mask formula correctness? |  | need to check correctness
|  | 10.1.2 |  |  | Receiver | Close
11 |  |  |  |  | Link Budget | Open | [Prev. Editor’s note: Open items: Should maximum range (link budget) be used as a performance metric for proposal comparison or not? Also need to determine how to use the building/vehicular penetration loss numbers for different environments] Option1/2/3/4 | OP1:decide max data rate for cell size OP2: descrive system parameters OP3: no description for max data rate and cell size OP4: descrive system parameters and calculate Eb/No
12 |  |  |  |  | Equipment Characteristics | -
| 12.1 |  |  |  | Antenna Characteristics | Close
| 12.2 |  |  |  | Hardware Characteristics | Close
| 12.3 |  |  |  | Deployment Characteristics | Close
13 |  |  |  |  | Output Metrics | Close
| 13.1 |  |  |  | System Capacity Metrics | Close
|  | 13.1.1 |  |  | Fixed load/coverage operating point: Service Distribution | Close
|  |  | 13.1.1.1 |  | Minimum Service Level | Close
|  | 13.1.2 |  |  | Aggregate Throughput | Close
|  | 13.1.3 |  |  | Network performance under Varying Load/Coverage | Close
|  | 13.1.4 |  |  | Computing Sustained Spectral Efficiency | Open | [Editor’s Note: Consistency needs to be checked with respect to the Requirement Document] | Four Options
| 13.2 |  |  |  | Coverage & Cell boundary data rate or Maximum Range | Open | [Prev. Editor’s note: The following 3 options are included corresponding to the options proposed for section 11: Link Budget, as proposed in ECCG CC contribution:“Eval_LinkBudget1r1.doc”.] Option 1-4: Link budget option1-4 | OP1 coverage /OP3 max data rate/ OP2&4 not need for section
14 |  |  |  |  | Payload Based Evaluation | Open | [Editor’s Note: Need further discussion on how we are going to use payload based evaluation criteria]
| 14.1 |  |  |  | Capacity performance evaluation criteria | Open | Channel spacing: 1.25MHz and 5MHz [Prev. Editor Note: Example of inconsistency, see Section 16 below] [NOTE the Alternate text for section 14.1was proposed by prev. editor as follows:] | rearrangement conditions
| 14.2 |  |  |  | Payload transmission delay evaluation criteria | Close
15 |  |  |  |  | Fairness criteria | Open | Editor’s Note: If no contributions are received addressing the text/notes that follow in Brackets then we should delete the text.[The proposals will also be evaluated on the basis of additional fairness metrics. The details of the additional fairness metrics are TBD (Editor’s note: for example IEEE C802.20-04/05 for other traffic types.)].
16 |  |  |  |  | Simulation and Evaluation of various block assignments | Open | [Prev.Editor’s note: text needs to be provided for unpaired block assignments] |  | Please see Joanne's contribution 1. Proposed Edits to the Evaluation Criteria Document (090705).doc
17 |  |  |  |  | references | Close
18 |  |  |  |  | Appendix A: Definition of terms | Close
19 |  |  |  |  | Appendix B: 19Cell Wrap-around Implementation | Open | All remaining text and diagrams in this section may not be correct. The Editor’s Notes on agreement in Session 13 are not clear.
20 |  |  |  |  | Appendix C: Fixed user locations for system level calibration | Close